## Supabase Snippet Daily Task Det
day_number | floor | process | assigned_trade | planned_remaining | is_valid | task_status | initial_production_rate | actual_efficiency | remain_work | is_rework | today_workload | predecessor_processes | pre_remain_work | trade_available | prerequisites_completed | can_start
0 | 1 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | null | Partition phase 2 | 19 | 1 | FALSE | FALSE
0 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | null | Partition phase 2 | 19 | 1 | FALSE | FALSE
0 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | null | Partition phase 2 | 19 | 1 | FALSE | FALSE
0 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | null | Partition phase 2 | 19 | 1 | FALSE | FALSE
0 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | null | Partition phase 2 | 19 | 1 | FALSE | FALSE
0 | 1 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | null | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
0 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | null | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
0 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | null | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
0 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | null | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
0 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | null | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
0 | 1 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | null | null | null | 1 | TRUE | TRUE
0 | 2 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | null | null | null | 1 | TRUE | TRUE
0 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | null | null | null | 1 | TRUE | TRUE
0 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | null | null | null | 1 | TRUE | TRUE
0 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | null | null | null | 1 | TRUE | TRUE
0 | 1 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | null | null | null | 1 | TRUE | TRUE
0 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | null | null | null | 1 | TRUE | TRUE
0 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | null | null | null | 1 | TRUE | TRUE
0 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | null | null | null | 1 | TRUE | TRUE
0 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | null | null | null | 1 | TRUE | TRUE
0 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | null | Pipes in the wall | 175 | 1 | FALSE | FALSE
0 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | null | Pipes in the wall | 175 | 1 | FALSE | FALSE
0 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | null | Pipes in the wall | 175 | 1 | FALSE | FALSE
0 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | null | Pipes in the wall | 175 | 1 | FALSE | FALSE
0 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | null | Pipes in the wall | 175 | 1 | FALSE | FALSE
0 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | null | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
0 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | null | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
0 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | null | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
0 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | null | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
0 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | null | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
0 | 1 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | null | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | null | Partition phase 1 | 818 | 1 | FALSE | FALSE
0 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | null | Partition phase 1 | 818 | 1 | FALSE | FALSE
0 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | null | Partition phase 1 | 818 | 1 | FALSE | FALSE
0 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | null | Partition phase 1 | 818 | 1 | FALSE | FALSE
0 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | null | Partition phase 1 | 818 | 1 | FALSE | FALSE
0 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | null | Partition phase 3 | 216 | 1 | FALSE | FALSE
0 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | null | Partition phase 3 | 216 | 1 | FALSE | FALSE
0 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | null | Partition phase 3 | 216 | 1 | FALSE | FALSE
0 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | null | Partition phase 3 | 216 | 1 | FALSE | FALSE
0 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | null | Partition phase 3 | 216 | 1 | FALSE | FALSE
1 | 1 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 122 | 1 | FALSE | FALSE
1 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
1 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
1 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
1 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
1 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
1 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
1 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
1 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
1 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
1 | 1 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
1 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
1 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
1 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
1 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
1 | 1 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 32 | 122 | FALSE | 32 | null | null | 0 | TRUE | FALSE
1 | 2 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
1 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
1 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
1 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
1 | 1 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 58 | 760 | FALSE | 58 | null | null | 0 | TRUE | FALSE
1 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
1 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
1 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
1 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
1 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
1 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
1 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
1 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
1 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
1 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
1 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
1 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
1 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
1 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
1 | 1 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 122 | 1 | FALSE | FALSE
1 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
1 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
1 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
1 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
1 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 760 | 1 | FALSE | FALSE
1 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
1 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
1 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
1 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
1 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
1 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
1 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
1 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
1 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
2 | 1 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 90 | 1 | FALSE | FALSE
2 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
2 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
2 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
2 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
2 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
2 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
2 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
2 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
2 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
2 | 1 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
2 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
2 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
2 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
2 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
2 | 1 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 32 | 90 | FALSE | 32 | null | null | 0 | TRUE | FALSE
2 | 2 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
2 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
2 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
2 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
2 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 51 | 709 | FALSE | 51 | null | null | 0 | TRUE | FALSE
2 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
2 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
2 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
2 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
2 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
2 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
2 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
2 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
2 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
2 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
2 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
2 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
2 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
2 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
2 | 1 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 90 | 1 | FALSE | FALSE
2 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
2 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
2 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
2 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
2 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 709 | 1 | FALSE | FALSE
2 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
2 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
2 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
2 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
2 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
2 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
2 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
2 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
2 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
3 | 1 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 58 | 1 | FALSE | FALSE
3 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
3 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
3 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
3 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
3 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
3 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
3 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
3 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
3 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
3 | 1 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
3 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
3 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
3 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
3 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
3 | 1 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 32 | 58 | FALSE | 32 | null | null | 0 | TRUE | FALSE
3 | 2 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
3 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
3 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
3 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
3 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 655 | FALSE | 54 | null | null | 0 | TRUE | FALSE
3 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
3 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
3 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
3 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
3 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
3 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
3 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
3 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
3 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
3 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
3 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
3 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
3 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
3 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
3 | 1 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 58 | 1 | FALSE | FALSE
3 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
3 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
3 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
3 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
3 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 655 | 1 | FALSE | FALSE
3 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
3 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
3 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
3 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
3 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
3 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
3 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
3 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
3 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
4 | 1 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 25 | 1 | FALSE | FALSE
4 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
4 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
4 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
4 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
4 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
4 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
4 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
4 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
4 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
4 | 1 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
4 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
4 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
4 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
4 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
4 | 1 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 33 | 25 | FALSE | 33 | null | null | 0 | TRUE | FALSE
4 | 2 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
4 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
4 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
4 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
4 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 51 | 604 | FALSE | 51 | null | null | 0 | TRUE | FALSE
4 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
4 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
4 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
4 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
4 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
4 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
4 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
4 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
4 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
4 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
4 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
4 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
4 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
4 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
4 | 1 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 25 | 1 | FALSE | FALSE
4 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
4 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
4 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
4 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
4 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 604 | 1 | FALSE | FALSE
4 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
4 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
4 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
4 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
4 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
4 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
4 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
4 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
4 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
5 | 1 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
5 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
5 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
5 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
5 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
5 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
5 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
5 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
5 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
5 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
5 | 1 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
5 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
5 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
5 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
5 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
5 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | 34 | 0 | FALSE | 25 | null | null | 1 | TRUE | FALSE
5 | 2 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
5 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
5 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
5 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
5 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 60 | 544 | FALSE | 60 | null | null | 0 | TRUE | FALSE
5 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
5 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
5 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
5 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
5 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
5 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
5 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
5 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
5 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
5 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
5 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
5 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
5 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
5 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
5 | 1 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
5 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
5 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
5 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
5 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
5 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 544 | 1 | FALSE | FALSE
5 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
5 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
5 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
5 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
5 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
5 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
5 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
5 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
5 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
6 | 1 | Electric conduits in the floor | Electricity | 74 | FALSE | in_progress | 51 | 56 | 18 | FALSE | 56 | Gravel base layer | 0 | 0 | TRUE | FALSE
6 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 121 | 0 | FALSE | FALSE
6 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
6 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
6 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
6 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
6 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
6 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
6 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
6 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
6 | 1 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 18, 31 | 1 | FALSE | FALSE
6 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
6 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
6 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
6 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
6 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
6 | 2 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 33 | 121 | FALSE | 33 | null | null | 0 | TRUE | FALSE
6 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
6 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
6 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
6 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 0 | 544 | TRUE | 0 | null | null | 0 | TRUE | FALSE
6 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
6 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
6 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
6 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
6 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
6 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
6 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
6 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
6 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
6 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
6 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
6 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
6 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
6 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
6 | 1 | Pipes in the floor | Plumbing | 103 | FALSE | in_progress | 69 | 72 | 31 | FALSE | 72 | Gravel base layer | 0 | 0 | TRUE | FALSE
6 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 121 | 0 | FALSE | FALSE
6 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
6 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
6 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
6 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 544 | 0 | FALSE | FALSE
6 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
6 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
6 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
6 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
6 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
6 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
6 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
6 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
6 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
7 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | 49 | 0 | FALSE | 18 | Gravel base layer | 0 | 1 | TRUE | FALSE
7 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 84 | 1 | FALSE | FALSE
7 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
7 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
7 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
7 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
7 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
7 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
7 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
7 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
7 | 1 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | TRUE
7 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
7 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
7 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
7 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
7 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
7 | 2 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 37 | 84 | FALSE | 37 | null | null | 0 | TRUE | FALSE
7 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
7 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
7 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
7 | 1 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 0 | 544 | TRUE | 0 | null | null | 0 | TRUE | FALSE
7 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
7 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
7 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
7 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
7 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
7 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
7 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
7 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
7 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
7 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
7 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
7 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
7 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
7 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
7 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | 66 | 0 | FALSE | 31 | Gravel base layer | 0 | 1 | TRUE | FALSE
7 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 84 | 1 | FALSE | FALSE
7 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
7 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
7 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
7 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 544 | 1 | FALSE | FALSE
7 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
7 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
7 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
7 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
7 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
7 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
7 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
7 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
7 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
8 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
8 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 49 | 1 | FALSE | FALSE
8 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
8 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
8 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
8 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
8 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
8 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
8 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
8 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
8 | 1 | Floor tiling | Tiling | 661 | FALSE | in_progress | 62 | 68 | 593 | FALSE | 68 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
8 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
8 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
8 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
8 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
8 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
8 | 2 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 35 | 49 | FALSE | 35 | null | null | 0 | TRUE | FALSE
8 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
8 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
8 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
8 | 1 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 56 | 488 | FALSE | 56 | null | null | 0 | TRUE | FALSE
8 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
8 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
8 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
8 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
8 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
8 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
8 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
8 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
8 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
8 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
8 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
8 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
8 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
8 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
8 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
8 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 49 | 1 | FALSE | FALSE
8 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
8 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
8 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
8 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 488 | 1 | FALSE | FALSE
8 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
8 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
8 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
8 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
8 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
8 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
8 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
8 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
8 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
9 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
9 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 14 | 1 | FALSE | FALSE
9 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
9 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
9 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
9 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
9 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
9 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
9 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
9 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
9 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 61 | 532 | FALSE | 61 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
9 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
9 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
9 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
9 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
9 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
9 | 2 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 35 | 14 | FALSE | 35 | null | null | 0 | TRUE | FALSE
9 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
9 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
9 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
9 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 50 | 438 | FALSE | 50 | null | null | 0 | TRUE | FALSE
9 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
9 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
9 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
9 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
9 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
9 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
9 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
9 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
9 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
9 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
9 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
9 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
9 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
9 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
9 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
9 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 14 | 1 | FALSE | FALSE
9 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
9 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
9 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
9 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 438 | 1 | FALSE | FALSE
9 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
9 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
9 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
9 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
9 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
9 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
9 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
9 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
9 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
10 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
10 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
10 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
10 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
10 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
10 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
10 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
10 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
10 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
10 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
10 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 66 | 466 | FALSE | 66 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
10 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
10 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
10 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
10 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
10 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
10 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | 37 | 0 | FALSE | 14 | null | null | 1 | TRUE | FALSE
10 | 3 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
10 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
10 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
10 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 58 | 380 | FALSE | 58 | null | null | 0 | TRUE | FALSE
10 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
10 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
10 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
10 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
10 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
10 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
10 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
10 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
10 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
10 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
10 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
10 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
10 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
10 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
10 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
10 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
10 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
10 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
10 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
10 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 380 | 1 | FALSE | FALSE
10 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
10 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
10 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
10 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
10 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
10 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
10 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
10 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
10 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
11 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
11 | 2 | Electric conduits in the floor | Electricity | 74 | FALSE | in_progress | 51 | 47 | 27 | FALSE | 47 | Gravel base layer | 0 | 0 | TRUE | FALSE
11 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 119 | 0 | FALSE | FALSE
11 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
11 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
11 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
11 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
11 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
11 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
11 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
11 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 66 | 400 | FALSE | 66 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
11 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 27, 103 | 0 | FALSE | FALSE
11 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
11 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
11 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
11 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
11 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
11 | 3 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 35 | 119 | FALSE | 35 | null | null | 0 | TRUE | FALSE
11 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
11 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
11 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 60 | 320 | FALSE | 60 | null | null | 0 | TRUE | FALSE
11 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
11 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
11 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
11 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
11 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
11 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
11 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
11 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
11 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
11 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
11 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
11 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
11 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
11 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
11 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
11 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | in_progress | 69 | 0 | 103 | TRUE | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
11 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 119 | 0 | FALSE | FALSE
11 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
11 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
11 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 320 | 0 | FALSE | FALSE
11 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
11 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
11 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
11 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
11 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
11 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
11 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
11 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
11 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
12 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
12 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | 53 | 0 | FALSE | 27 | Gravel base layer | 0 | 1 | TRUE | FALSE
12 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 119 | 1 | FALSE | FALSE
12 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
12 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
12 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
12 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
12 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
12 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
12 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
12 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 57 | 343 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
12 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 32 | 0 | FALSE | FALSE
12 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
12 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
12 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
12 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
12 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
12 | 3 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 0 | 119 | TRUE | 0 | null | null | 0 | TRUE | FALSE
12 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
12 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
12 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 52 | 268 | FALSE | 52 | null | null | 0 | TRUE | FALSE
12 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
12 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
12 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
12 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
12 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
12 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
12 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
12 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
12 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
12 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
12 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
12 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
12 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
12 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
12 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
12 | 2 | Pipes in the floor | Plumbing | 103 | FALSE | in_progress | 69 | 71 | 32 | FALSE | 71 | Gravel base layer | 0 | 0 | TRUE | FALSE
12 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 119 | 0 | FALSE | FALSE
12 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
12 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
12 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 268 | 0 | FALSE | FALSE
12 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
12 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
12 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
12 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
12 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
12 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
12 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
12 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
12 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
13 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
13 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
13 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 119 | 1 | FALSE | FALSE
13 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
13 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
13 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
13 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
13 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
13 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
13 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
13 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 64 | 279 | FALSE | 64 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
13 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
13 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
13 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
13 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
13 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
13 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
13 | 3 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 0 | 119 | TRUE | 0 | null | null | 0 | TRUE | FALSE
13 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
13 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
13 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 214 | FALSE | 54 | null | null | 0 | TRUE | FALSE
13 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
13 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
13 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
13 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
13 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
13 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
13 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
13 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
13 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
13 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
13 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
13 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
13 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
13 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
13 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
13 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | 65 | 0 | FALSE | 32 | Gravel base layer | 0 | 1 | TRUE | FALSE
13 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 119 | 1 | FALSE | FALSE
13 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
13 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
13 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 214 | 1 | FALSE | FALSE
13 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
13 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
13 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
13 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
13 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
13 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
13 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
13 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
13 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
14 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
14 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
14 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 83 | 1 | FALSE | FALSE
14 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
14 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
14 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
14 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
14 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
14 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
14 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
14 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 67 | 212 | FALSE | 67 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
14 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
14 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
14 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
14 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
14 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
14 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
14 | 3 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 36 | 83 | FALSE | 36 | null | null | 0 | TRUE | FALSE
14 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
14 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
14 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 51 | 163 | FALSE | 51 | null | null | 0 | TRUE | FALSE
14 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
14 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
14 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
14 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
14 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
14 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
14 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
14 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
14 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
14 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
14 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
14 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
14 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
14 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
14 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
14 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
14 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 83 | 1 | FALSE | FALSE
14 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
14 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
14 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 163 | 1 | FALSE | FALSE
14 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
14 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
14 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
14 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
14 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
14 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
14 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
14 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
14 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
15 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
15 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
15 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 48 | 1 | FALSE | FALSE
15 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
15 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
15 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
15 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
15 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
15 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
15 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
15 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 65 | 147 | FALSE | 65 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
15 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
15 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
15 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
15 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
15 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
15 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
15 | 3 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 35 | 48 | FALSE | 35 | null | null | 0 | TRUE | FALSE
15 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
15 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
15 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 52 | 111 | FALSE | 52 | null | null | 0 | TRUE | FALSE
15 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
15 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
15 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
15 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
15 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
15 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
15 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
15 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
15 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
15 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
15 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
15 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
15 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
15 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
15 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
15 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
15 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 48 | 1 | FALSE | FALSE
15 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
15 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
15 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 111 | 1 | FALSE | FALSE
15 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
15 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
15 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
15 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
15 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
15 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
15 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
15 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
15 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
16 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
16 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
16 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 15 | 1 | FALSE | FALSE
16 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
16 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
16 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
16 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
16 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
16 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
16 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
16 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 56 | 91 | FALSE | 56 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
16 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
16 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
16 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
16 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
16 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
16 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
16 | 3 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 33 | 15 | FALSE | 33 | null | null | 0 | TRUE | FALSE
16 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
16 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
16 | 1 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 59 | 52 | FALSE | 59 | null | null | 0 | TRUE | FALSE
16 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
16 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
16 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
16 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
16 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
16 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
16 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
16 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
16 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
16 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
16 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
16 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
16 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
16 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
16 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
16 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
16 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 15 | 1 | FALSE | FALSE
16 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
16 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
16 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 52 | 1 | FALSE | FALSE
16 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
16 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
16 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
16 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
16 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
16 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
16 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
16 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
16 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
17 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
17 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
17 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
17 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
17 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
17 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
17 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
17 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
17 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
17 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
17 | 1 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 60 | 31 | FALSE | 60 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
17 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
17 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
17 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
17 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
17 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
17 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
17 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | 31 | 0 | FALSE | 15 | null | null | 1 | TRUE | FALSE
17 | 4 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
17 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
17 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | 59 | 0 | FALSE | 52 | null | null | 1 | TRUE | FALSE
17 | 2 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
17 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
17 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
17 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
17 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
17 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
17 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
17 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
17 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
17 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
17 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
17 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
17 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
17 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
17 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
17 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
17 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
17 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
17 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
17 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | TRUE
17 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
17 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
17 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
17 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
17 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
17 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
17 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
17 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
17 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
18 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
18 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
18 | 3 | Electric conduits in the floor | Electricity | 74 | FALSE | in_progress | 51 | 50 | 24 | FALSE | 50 | Gravel base layer | 0 | 0 | TRUE | FALSE
18 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 121 | 0 | FALSE | FALSE
18 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
18 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
18 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
18 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
18 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
18 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
18 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | 65 | 0 | FALSE | 31 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
18 | 2 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | TRUE
18 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 24, 103 | 1 | FALSE | FALSE
18 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
18 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
18 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
18 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
18 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
18 | 4 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 33 | 121 | FALSE | 33 | null | null | 0 | TRUE | FALSE
18 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
18 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
18 | 2 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 50 | 768 | FALSE | 50 | null | null | 0 | TRUE | FALSE
18 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
18 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
18 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
18 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 138 | 0 | FALSE | FALSE
18 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
18 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
18 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
18 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
18 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
18 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
18 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
18 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
18 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
18 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
18 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
18 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
18 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 121 | 0 | FALSE | FALSE
18 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
18 | 1 | Pipes in the wall | Plumbing | 175 | FALSE | in_progress | 37 | 37 | 138 | FALSE | 37 | Partition phase 1 | 0 | 0 | TRUE | FALSE
18 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 768 | 0 | FALSE | FALSE
18 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
18 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
18 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
18 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
18 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
18 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
18 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
18 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
19 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
19 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
19 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | 48 | 0 | FALSE | 24 | Gravel base layer | 0 | 1 | TRUE | FALSE
19 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 85 | 1 | FALSE | FALSE
19 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
19 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
19 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
19 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
19 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
19 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
19 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
19 | 2 | Floor tiling | Tiling | 661 | FALSE | in_progress | 62 | 68 | 593 | FALSE | 68 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
19 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 103 | 0 | FALSE | FALSE
19 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
19 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
19 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
19 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
19 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
19 | 4 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 36 | 85 | FALSE | 36 | null | null | 0 | TRUE | FALSE
19 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
19 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
19 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 52 | 716 | FALSE | 52 | null | null | 0 | TRUE | FALSE
19 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
19 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
19 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
19 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 97 | 0 | FALSE | FALSE
19 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
19 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
19 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
19 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
19 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
19 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
19 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
19 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
19 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
19 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
19 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
19 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
19 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 85 | 0 | FALSE | FALSE
19 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
19 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 41 | 97 | FALSE | 41 | Partition phase 1 | 0 | 0 | TRUE | FALSE
19 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 716 | 0 | FALSE | FALSE
19 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
19 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
19 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
19 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
19 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
19 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
19 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
19 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
20 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
20 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
20 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
20 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 54 | 1 | FALSE | FALSE
20 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
20 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
20 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
20 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
20 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
20 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
20 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
20 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 68 | 525 | FALSE | 68 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
20 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 103 | 0 | FALSE | FALSE
20 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
20 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
20 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
20 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
20 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
20 | 4 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 31 | 54 | FALSE | 31 | null | null | 0 | TRUE | FALSE
20 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
20 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
20 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 51 | 665 | FALSE | 51 | null | null | 0 | TRUE | FALSE
20 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
20 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
20 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
20 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 61 | 0 | FALSE | FALSE
20 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
20 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
20 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
20 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
20 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
20 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
20 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
20 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
20 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
20 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
20 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
20 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
20 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 54 | 0 | FALSE | FALSE
20 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
20 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 36 | 61 | FALSE | 36 | Partition phase 1 | 0 | 0 | TRUE | FALSE
20 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 665 | 0 | FALSE | FALSE
20 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
20 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
20 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
20 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
20 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
20 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
20 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
20 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
21 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
21 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
21 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
21 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 54 | 1 | FALSE | FALSE
21 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
21 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
21 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
21 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
21 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
21 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
21 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
21 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 60 | 465 | FALSE | 60 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
21 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 103 | 0 | FALSE | FALSE
21 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
21 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
21 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
21 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
21 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
21 | 4 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 0 | 54 | TRUE | 0 | null | null | 0 | TRUE | FALSE
21 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
21 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
21 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 53 | 612 | FALSE | 53 | null | null | 0 | TRUE | FALSE
21 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
21 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
21 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
21 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 23 | 0 | FALSE | FALSE
21 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
21 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
21 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
21 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
21 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
21 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
21 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
21 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
21 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
21 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
21 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
21 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
21 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 54 | 0 | FALSE | FALSE
21 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
21 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 38 | 23 | FALSE | 38 | Partition phase 1 | 0 | 0 | TRUE | FALSE
21 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 612 | 0 | FALSE | FALSE
21 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
21 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
21 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
21 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
21 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
21 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
21 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
21 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
22 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
22 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
22 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
22 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 54 | 1 | FALSE | FALSE
22 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
22 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
22 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
22 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
22 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
22 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
22 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
22 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 67 | 398 | FALSE | 67 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
22 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 103 | 0 | FALSE | FALSE
22 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
22 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
22 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
22 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
22 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
22 | 4 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 0 | 54 | TRUE | 0 | null | null | 0 | TRUE | FALSE
22 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
22 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
22 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 52 | 560 | FALSE | 52 | null | null | 0 | TRUE | FALSE
22 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
22 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
22 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
22 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
22 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
22 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
22 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
22 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
22 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
22 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
22 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
22 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
22 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
22 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
22 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
22 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
22 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 54 | 1 | FALSE | FALSE
22 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
22 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | 37 | 0 | FALSE | 23 | Partition phase 1 | 0 | 1 | TRUE | FALSE
22 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 560 | 1 | FALSE | FALSE
22 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
22 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
22 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
22 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
22 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
22 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
22 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
22 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
23 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
23 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
23 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
23 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 54 | 1 | FALSE | FALSE
23 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
23 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
23 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
23 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
23 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
23 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
23 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
23 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 0 | 398 | TRUE | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
23 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 28 | 0 | FALSE | FALSE
23 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
23 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
23 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
23 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
23 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
23 | 4 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 0 | 54 | TRUE | 0 | null | null | 0 | TRUE | FALSE
23 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
23 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
23 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 55 | 505 | FALSE | 55 | null | null | 0 | TRUE | FALSE
23 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
23 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
23 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
23 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
23 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
23 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
23 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
23 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
23 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
23 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
23 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
23 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
23 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
23 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
23 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
23 | 3 | Pipes in the floor | Plumbing | 103 | FALSE | in_progress | 69 | 75 | 28 | FALSE | 75 | Gravel base layer | 0 | 0 | TRUE | FALSE
23 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 54 | 0 | FALSE | FALSE
23 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 0 | FALSE | FALSE
23 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
23 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 505 | 0 | FALSE | FALSE
23 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
23 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
23 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
23 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
23 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
23 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
23 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
23 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
24 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
24 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
24 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
24 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 20 | 1 | FALSE | FALSE
24 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
24 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
24 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
24 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
24 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
24 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
24 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
24 | 2 | Floor tiling | Tiling | 661 | FALSE | in_progress | 62 | 67 | 331 | FALSE | 67 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
24 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
24 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
24 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
24 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
24 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
24 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
24 | 4 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 34 | 20 | FALSE | 34 | null | null | 0 | TRUE | FALSE
24 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 0 | TRUE | FALSE
24 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
24 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 57 | 448 | FALSE | 57 | null | null | 0 | TRUE | FALSE
24 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
24 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
24 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
24 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
24 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
24 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
24 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
24 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
24 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
24 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
24 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
24 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
24 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
24 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
24 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
24 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | 64 | 0 | FALSE | 28 | Gravel base layer | 0 | 1 | TRUE | FALSE
24 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 20 | 1 | FALSE | FALSE
24 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
24 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
24 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 448 | 1 | FALSE | FALSE
24 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
24 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
24 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
24 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
24 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
24 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
24 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
24 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
25 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
25 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
25 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
25 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
25 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
25 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
25 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
25 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
25 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
25 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
25 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
25 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 57 | 274 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
25 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
25 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
25 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
25 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
25 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
25 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
25 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | 31 | 0 | FALSE | 20 | null | null | 1 | TRUE | FALSE
25 | 5 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | 0 | null | null | 1 | TRUE | TRUE
25 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
25 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 394 | FALSE | 54 | null | null | 0 | TRUE | FALSE
25 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
25 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
25 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
25 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
25 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
25 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
25 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
25 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
25 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
25 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
25 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
25 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
25 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
25 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
25 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
25 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
25 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
25 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 154 | 1 | FALSE | FALSE
25 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
25 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 394 | 1 | FALSE | FALSE
25 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
25 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
25 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
25 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
25 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
25 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
25 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
25 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
26 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
26 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
26 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
26 | 4 | Electric conduits in the floor | Electricity | 74 | FALSE | in_progress | 51 | 48 | 26 | FALSE | 48 | Gravel base layer | 0 | 0 | TRUE | FALSE
26 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 121 | 0 | FALSE | FALSE
26 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
26 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
26 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
26 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
26 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
26 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
26 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 56 | 218 | FALSE | 56 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
26 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
26 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 26, 28 | 0 | FALSE | FALSE
26 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
26 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
26 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
26 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
26 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
26 | 5 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 33 | 121 | FALSE | 33 | null | null | 0 | TRUE | FALSE
26 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
26 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 52 | 342 | FALSE | 52 | null | null | 0 | TRUE | FALSE
26 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
26 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
26 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
26 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
26 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
26 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
26 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
26 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
26 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
26 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
26 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
26 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
26 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
26 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
26 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
26 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
26 | 4 | Pipes in the floor | Plumbing | 103 | FALSE | in_progress | 69 | 75 | 28 | FALSE | 75 | Gravel base layer | 0 | 0 | TRUE | FALSE
26 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 121 | 0 | FALSE | FALSE
26 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
26 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 342 | 0 | FALSE | FALSE
26 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
26 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
26 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
26 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
26 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
26 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
26 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
26 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
27 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
27 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
27 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
27 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | 49 | 0 | FALSE | 26 | Gravel base layer | 0 | 1 | TRUE | FALSE
27 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 84 | 1 | FALSE | FALSE
27 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
27 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
27 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
27 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
27 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
27 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
27 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 65 | 153 | FALSE | 65 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
27 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
27 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
27 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
27 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
27 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
27 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
27 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
27 | 5 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 37 | 84 | FALSE | 37 | null | null | 0 | TRUE | FALSE
27 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
27 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 60 | 282 | FALSE | 60 | null | null | 0 | TRUE | FALSE
27 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
27 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
27 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
27 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
27 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
27 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
27 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
27 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
27 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
27 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
27 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
27 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
27 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
27 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
27 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
27 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
27 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | 71 | 0 | FALSE | 28 | Gravel base layer | 0 | 1 | TRUE | FALSE
27 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 84 | 1 | FALSE | FALSE
27 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
27 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 282 | 1 | FALSE | FALSE
27 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
27 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
27 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
27 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
27 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
27 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
27 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
27 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
28 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
28 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
28 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
28 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
28 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 49 | 1 | FALSE | FALSE
28 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
28 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
28 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
28 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
28 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
28 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
28 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 63 | 90 | FALSE | 63 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
28 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
28 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
28 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
28 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
28 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
28 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
28 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
28 | 5 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 35 | 49 | FALSE | 35 | null | null | 0 | TRUE | FALSE
28 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
28 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 228 | FALSE | 54 | null | null | 0 | TRUE | FALSE
28 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
28 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
28 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
28 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
28 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
28 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
28 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
28 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
28 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
28 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
28 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
28 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
28 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
28 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
28 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
28 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
28 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
28 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 49 | 1 | FALSE | FALSE
28 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
28 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 228 | 1 | FALSE | FALSE
28 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
28 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
28 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
28 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
28 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
28 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
28 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
28 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
29 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
29 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
29 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
29 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
29 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 15 | 1 | FALSE | FALSE
29 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
29 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
29 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
29 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
29 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
29 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
29 | 2 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 59 | 31 | FALSE | 59 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
29 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
29 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
29 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 0 | FALSE | FALSE
29 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
29 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
29 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
29 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
29 | 5 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 34 | 15 | FALSE | 34 | null | null | 0 | TRUE | FALSE
29 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
29 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 52 | 176 | FALSE | 52 | null | null | 0 | TRUE | FALSE
29 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
29 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
29 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
29 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
29 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
29 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
29 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
29 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
29 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
29 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
29 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
29 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
29 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
29 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
29 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
29 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
29 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
29 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 15 | 1 | FALSE | FALSE
29 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
29 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 176 | 1 | FALSE | FALSE
29 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
29 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
29 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
29 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
29 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
29 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
29 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
29 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
30 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
30 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
30 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
30 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
30 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | pending | 51 | null | 74 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
30 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
30 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
30 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
30 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
30 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
30 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
30 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | 57 | 0 | FALSE | 31 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
30 | 3 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | TRUE
30 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | TRUE
30 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
30 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
30 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
30 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
30 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
30 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | 36 | 0 | FALSE | 15 | null | null | 1 | TRUE | FALSE
30 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
30 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 0 | 176 | TRUE | 0 | null | null | 0 | TRUE | FALSE
30 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
30 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
30 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
30 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
30 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
30 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
30 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
30 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
30 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
30 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
30 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
30 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
30 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
30 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
30 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
30 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
30 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
30 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | pending | 69 | null | 103 | null | 0 | Gravel base layer | 0 | 1 | TRUE | TRUE
30 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
30 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 176 | 1 | FALSE | FALSE
30 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
30 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
30 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
30 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
30 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
30 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
30 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
30 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
31 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 5 | Electric conduits in the floor | Electricity | 74 | FALSE | in_progress | 51 | 54 | 20 | FALSE | 54 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
31 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
31 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
31 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
31 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
31 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
31 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
31 | 3 | Floor tiling | Tiling | 661 | FALSE | in_progress | 62 | 62 | 599 | FALSE | 62 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
31 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
31 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 20, 29 | 0 | FALSE | FALSE
31 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
31 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
31 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
31 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
31 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
31 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
31 | 2 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 50 | 126 | FALSE | 50 | null | null | 0 | TRUE | FALSE
31 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
31 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
31 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
31 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
31 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
31 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
31 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
31 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
31 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
31 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
31 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
31 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
31 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
31 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 5 | Pipes in the floor | Plumbing | 103 | FALSE | in_progress | 69 | 74 | 29 | FALSE | 74 | Gravel base layer | 0 | 0 | TRUE | FALSE
31 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
31 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 126 | 0 | FALSE | FALSE
31 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
31 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
31 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
31 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
31 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
31 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
31 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
31 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
32 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | 55 | 0 | FALSE | 20 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
32 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
32 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
32 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
32 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
32 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
32 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
32 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 57 | 542 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
32 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
32 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
32 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
32 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
32 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
32 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
32 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
32 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
32 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 72 | FALSE | 54 | null | null | 0 | TRUE | FALSE
32 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
32 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
32 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
32 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
32 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
32 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
32 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
32 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
32 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
32 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
32 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
32 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
32 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
32 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | 71 | 0 | FALSE | 29 | Gravel base layer | 0 | 1 | TRUE | FALSE
32 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
32 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 72 | 1 | FALSE | FALSE
32 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
32 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
32 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
32 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
32 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
32 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
32 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
32 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
33 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
33 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
33 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
33 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
33 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
33 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
33 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
33 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 58 | 484 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
33 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
33 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
33 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
33 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
33 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
33 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
33 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
33 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
33 | 2 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 51 | 21 | FALSE | 51 | null | null | 0 | TRUE | FALSE
33 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
33 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
33 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
33 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
33 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
33 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
33 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
33 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
33 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
33 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
33 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
33 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
33 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
33 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
33 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
33 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 21 | 1 | FALSE | FALSE
33 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
33 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
33 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
33 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
33 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
33 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
33 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
33 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
34 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
34 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
34 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
34 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
34 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
34 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
34 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
34 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 61 | 423 | FALSE | 61 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
34 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
34 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
34 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
34 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
34 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
34 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
34 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
34 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
34 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | 60 | 0 | FALSE | 21 | null | null | 1 | TRUE | FALSE
34 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
34 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
34 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
34 | 1 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | TRUE
34 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
34 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
34 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
34 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
34 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
34 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
34 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
34 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
34 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
34 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
34 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
34 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | TRUE
34 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
34 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
34 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
34 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
34 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
34 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
34 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
34 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
35 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
35 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
35 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
35 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
35 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
35 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | TRUE
35 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
35 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
35 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
35 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
35 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
35 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
35 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 0 | 423 | TRUE | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
35 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
35 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
35 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
35 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
35 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
35 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
35 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
35 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
35 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
35 | 3 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
35 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
35 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
35 | 1 | Partition phase 2 | Partition | 19 | FALSE | completed | 51 | 19 | 0 | FALSE | 19 | Pipes in the wall | 0 | 1 | TRUE | FALSE
35 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 135 | 1 | FALSE | FALSE
35 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
35 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
35 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
35 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
35 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
35 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
35 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
35 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
35 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
35 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
35 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
35 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
35 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
35 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
35 | 2 | Pipes in the wall | Plumbing | 175 | FALSE | in_progress | 37 | 40 | 135 | FALSE | 40 | Partition phase 1 | 0 | 0 | TRUE | FALSE
35 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
35 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
35 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
35 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
35 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
35 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
35 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
35 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
36 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 37 | 127 | FALSE | 37 | Partition phase 2 | 0 | 0 | TRUE | FALSE
36 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
36 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
36 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
36 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
36 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
36 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
36 | 3 | Floor tiling | Tiling | 661 | FALSE | in_progress | 62 | 59 | 364 | FALSE | 59 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
36 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
36 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
36 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
36 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
36 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
36 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
36 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
36 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
36 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
36 | 3 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 57 | 761 | FALSE | 57 | null | null | 0 | TRUE | FALSE
36 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
36 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
36 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
36 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 100 | 0 | FALSE | FALSE
36 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
36 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
36 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
36 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 127 | 0 | FALSE | FALSE
36 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
36 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
36 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
36 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
36 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
36 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
36 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 35 | 100 | FALSE | 35 | Partition phase 1 | 0 | 0 | TRUE | FALSE
36 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 761 | 0 | FALSE | FALSE
36 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
36 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
36 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
36 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
36 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
36 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
36 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
37 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 0 | 127 | TRUE | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
37 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
37 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
37 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
37 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
37 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
37 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
37 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 57 | 307 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
37 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
37 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
37 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
37 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
37 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
37 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
37 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
37 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
37 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
37 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 51 | 710 | FALSE | 51 | null | null | 0 | TRUE | FALSE
37 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
37 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
37 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
37 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 64 | 0 | FALSE | FALSE
37 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
37 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
37 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
37 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 127 | 0 | FALSE | FALSE
37 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
37 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
37 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
37 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
37 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
37 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
37 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 36 | 64 | FALSE | 36 | Partition phase 1 | 0 | 0 | TRUE | FALSE
37 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 710 | 0 | FALSE | FALSE
37 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
37 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
37 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
37 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
37 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
37 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
37 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
38 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 38 | 89 | FALSE | 38 | Partition phase 2 | 0 | 0 | TRUE | FALSE
38 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
38 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
38 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
38 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
38 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
38 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
38 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 58 | 249 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
38 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
38 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
38 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
38 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
38 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
38 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
38 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
38 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
38 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
38 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 59 | 651 | FALSE | 59 | null | null | 0 | TRUE | FALSE
38 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
38 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
38 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
38 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 29 | 0 | FALSE | FALSE
38 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
38 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
38 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
38 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 89 | 0 | FALSE | FALSE
38 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
38 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
38 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
38 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
38 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
38 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
38 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 35 | 29 | FALSE | 35 | Partition phase 1 | 0 | 0 | TRUE | FALSE
38 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 651 | 0 | FALSE | FALSE
38 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
38 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
38 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
38 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
38 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
38 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
38 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
39 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
39 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
39 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
39 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
39 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
39 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 45 | 44 | FALSE | 45 | Partition phase 2 | 0 | 0 | TRUE | FALSE
39 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
39 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
39 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
39 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
39 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
39 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
39 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 67 | 182 | FALSE | 67 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
39 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
39 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
39 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
39 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
39 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
39 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
39 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
39 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
39 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
39 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 56 | 595 | FALSE | 56 | null | null | 0 | TRUE | FALSE
39 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
39 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
39 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
39 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
39 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
39 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
39 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
39 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 44 | 0 | FALSE | FALSE
39 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
39 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
39 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
39 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
39 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
39 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
39 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
39 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
39 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
39 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
39 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | 40 | 0 | FALSE | 29 | Partition phase 1 | 0 | 1 | TRUE | FALSE
39 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 595 | 1 | FALSE | FALSE
39 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
39 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
39 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
39 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
39 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
39 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
39 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
40 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | 45 | 0 | FALSE | 44 | Partition phase 2 | 0 | 1 | TRUE | FALSE
40 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
40 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
40 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
40 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
40 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
40 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
40 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 0 | 182 | TRUE | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
40 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
40 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
40 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
40 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
40 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
40 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
40 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
40 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
40 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
40 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 0 | 595 | TRUE | 0 | null | null | 0 | TRUE | FALSE
40 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
40 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
40 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
40 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
40 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
40 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
40 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
40 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
40 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
40 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
40 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
40 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
40 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
40 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
40 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
40 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 595 | 1 | FALSE | FALSE
40 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
40 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
40 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
40 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
40 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
40 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
40 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
41 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
41 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
41 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
41 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
41 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
41 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
41 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
41 | 3 | Floor tiling | Tiling | 661 | FALSE | in_progress | 62 | 58 | 124 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
41 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
41 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
41 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
41 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
41 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
41 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
41 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
41 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
41 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
41 | 3 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 53 | 542 | FALSE | 53 | null | null | 0 | TRUE | FALSE
41 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
41 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
41 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
41 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
41 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
41 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
41 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
41 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
41 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
41 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
41 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
41 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
41 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
41 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
41 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
41 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 542 | 1 | FALSE | FALSE
41 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
41 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
41 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
41 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
41 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
41 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
41 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
42 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
42 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
42 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
42 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
42 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
42 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
42 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
42 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 60 | 64 | FALSE | 60 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
42 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
42 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
42 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
42 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
42 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
42 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
42 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
42 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
42 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
42 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 59 | 483 | FALSE | 59 | null | null | 0 | TRUE | FALSE
42 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
42 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
42 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
42 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
42 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
42 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
42 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
42 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
42 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
42 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
42 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
42 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
42 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
42 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
42 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
42 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 483 | 1 | FALSE | FALSE
42 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
42 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
42 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
42 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
42 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
42 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
42 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
43 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
43 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
43 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
43 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
43 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
43 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
43 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
43 | 3 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 58 | 6 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
43 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
43 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
43 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
43 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
43 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
43 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
43 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
43 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
43 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
43 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 50 | 433 | FALSE | 50 | null | null | 0 | TRUE | FALSE
43 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
43 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
43 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
43 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
43 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
43 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
43 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
43 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
43 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
43 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
43 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
43 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
43 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
43 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
43 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
43 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 433 | 1 | FALSE | FALSE
43 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
43 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
43 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
43 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
43 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
43 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
43 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
44 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
44 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
44 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
44 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
44 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
44 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
44 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
44 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | 59 | 0 | FALSE | 6 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
44 | 4 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | TRUE
44 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | TRUE
44 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
44 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
44 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
44 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
44 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
44 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
44 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
44 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 56 | 377 | FALSE | 56 | null | null | 0 | TRUE | FALSE
44 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
44 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
44 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
44 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
44 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
44 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
44 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
44 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
44 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
44 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
44 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
44 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
44 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
44 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
44 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
44 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 377 | 1 | FALSE | FALSE
44 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
44 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
44 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
44 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
44 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
44 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
44 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
45 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
45 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
45 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
45 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
45 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
45 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
45 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
45 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
45 | 4 | Floor tiling | Tiling | 661 | FALSE | in_progress | 62 | 57 | 604 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
45 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
45 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
45 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
45 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
45 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
45 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
45 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
45 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
45 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 50 | 327 | FALSE | 50 | null | null | 0 | TRUE | FALSE
45 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
45 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
45 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
45 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
45 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
45 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
45 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
45 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
45 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
45 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
45 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
45 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
45 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
45 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
45 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
45 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 327 | 1 | FALSE | FALSE
45 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
45 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
45 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
45 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
45 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
45 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
45 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
46 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
46 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
46 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
46 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
46 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
46 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
46 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
46 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
46 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 68 | 536 | FALSE | 68 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
46 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
46 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
46 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
46 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
46 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
46 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
46 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
46 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
46 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 0 | 327 | TRUE | 0 | null | null | 0 | TRUE | FALSE
46 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
46 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
46 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
46 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
46 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
46 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
46 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
46 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
46 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
46 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
46 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
46 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
46 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
46 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
46 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
46 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 327 | 1 | FALSE | FALSE
46 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
46 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
46 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
46 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
46 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
46 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
46 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
47 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
47 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
47 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
47 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
47 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
47 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
47 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
47 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
47 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 58 | 478 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
47 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
47 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
47 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
47 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
47 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
47 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
47 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
47 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
47 | 3 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 53 | 274 | FALSE | 53 | null | null | 0 | TRUE | FALSE
47 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
47 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
47 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
47 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
47 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
47 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
47 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
47 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
47 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
47 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
47 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
47 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
47 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
47 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
47 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
47 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 274 | 1 | FALSE | FALSE
47 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
47 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
47 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
47 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
47 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
47 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
47 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
48 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
48 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
48 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
48 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
48 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
48 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
48 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
48 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
48 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 66 | 412 | FALSE | 66 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
48 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
48 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
48 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
48 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
48 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
48 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
48 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
48 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
48 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 0 | 274 | TRUE | 0 | null | null | 0 | TRUE | FALSE
48 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
48 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
48 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
48 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
48 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
48 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
48 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
48 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
48 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
48 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
48 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
48 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
48 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
48 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
48 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
48 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 274 | 1 | FALSE | FALSE
48 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
48 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
48 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
48 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
48 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
48 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
48 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
49 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
49 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
49 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
49 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
49 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
49 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
49 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
49 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
49 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 66 | 346 | FALSE | 66 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
49 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
49 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
49 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
49 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
49 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
49 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
49 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
49 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
49 | 3 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 51 | 223 | FALSE | 51 | null | null | 0 | TRUE | FALSE
49 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
49 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
49 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
49 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
49 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
49 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
49 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
49 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
49 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
49 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
49 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
49 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
49 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
49 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
49 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
49 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 223 | 1 | FALSE | FALSE
49 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
49 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
49 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
49 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
49 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
49 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
49 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
50 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
50 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
50 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
50 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
50 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
50 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
50 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
50 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
50 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 61 | 285 | FALSE | 61 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
50 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
50 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
50 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
50 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
50 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
50 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
50 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
50 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
50 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 58 | 165 | FALSE | 58 | null | null | 0 | TRUE | FALSE
50 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
50 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
50 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
50 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
50 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
50 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
50 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
50 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
50 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
50 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
50 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
50 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
50 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
50 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
50 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
50 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 165 | 1 | FALSE | FALSE
50 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
50 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
50 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
50 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
50 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
50 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
50 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
51 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
51 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
51 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
51 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
51 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
51 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
51 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
51 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
51 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 61 | 224 | FALSE | 61 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
51 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
51 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
51 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
51 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
51 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
51 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
51 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
51 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
51 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 55 | 110 | FALSE | 55 | null | null | 0 | TRUE | FALSE
51 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
51 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
51 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
51 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
51 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
51 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
51 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
51 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
51 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
51 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
51 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
51 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
51 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
51 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
51 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
51 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 110 | 1 | FALSE | FALSE
51 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
51 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
51 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
51 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
51 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
51 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
51 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
52 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
52 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
52 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
52 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
52 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
52 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
52 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
52 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
52 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 64 | 160 | FALSE | 64 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
52 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
52 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
52 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
52 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
52 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
52 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
52 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
52 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
52 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 56 | 54 | FALSE | 56 | null | null | 0 | TRUE | FALSE
52 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
52 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
52 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
52 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
52 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
52 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
52 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
52 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
52 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
52 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
52 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
52 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
52 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
52 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
52 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
52 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 54 | 1 | FALSE | FALSE
52 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
52 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
52 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
52 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
52 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
52 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
52 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
53 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
53 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
53 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
53 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
53 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
53 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
53 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
53 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
53 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 61 | 99 | FALSE | 61 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
53 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
53 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
53 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
53 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
53 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
53 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
53 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
53 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
53 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 51 | 3 | FALSE | 51 | null | null | 0 | TRUE | FALSE
53 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
53 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
53 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
53 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
53 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
53 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
53 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
53 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
53 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
53 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
53 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
53 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
53 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
53 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
53 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
53 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 3 | 1 | FALSE | FALSE
53 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
53 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
53 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
53 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
53 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
53 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
53 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
54 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
54 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
54 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
54 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
54 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
54 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
54 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
54 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
54 | 4 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 64 | 35 | FALSE | 64 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
54 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
54 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
54 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
54 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
54 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
54 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
54 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
54 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
54 | 3 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 0 | 3 | TRUE | 0 | null | null | 0 | TRUE | FALSE
54 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
54 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
54 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
54 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
54 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
54 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
54 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
54 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
54 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
54 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
54 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
54 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
54 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
54 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
54 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
54 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 3 | 1 | FALSE | FALSE
54 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
54 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
54 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
54 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
54 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
54 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
54 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
55 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
55 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
55 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
55 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
55 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
55 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
55 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
55 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
55 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | 60 | 0 | FALSE | 35 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
55 | 5 | Floor tiling | Tiling | 661 | FALSE | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | TRUE
55 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
55 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
55 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
55 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
55 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
55 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
55 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
55 | 3 | Partition phase 1 | Partition | 818 | FALSE | completed | 55 | 53 | 0 | FALSE | 3 | null | null | 1 | TRUE | FALSE
55 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
55 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
55 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
55 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | TRUE
55 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
55 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
55 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
55 | 1 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | TRUE
55 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
55 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
55 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
55 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
55 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
55 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
55 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
55 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | TRUE
55 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
55 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
55 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
55 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
55 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
55 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
55 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
56 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
56 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
56 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
56 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
56 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
56 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
56 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
56 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
56 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
56 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
56 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
56 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
56 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
56 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
56 | 5 | Floor tiling | Tiling | 661 | FALSE | in_progress | 62 | 58 | 603 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
56 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
56 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
56 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
56 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
56 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
56 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
56 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
56 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
56 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
56 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
56 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
56 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
56 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 135 | 0 | FALSE | FALSE
56 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
56 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
56 | 1 | Partition phase 3 | Partition | 216 | FALSE | in_progress | 32 | 31 | 185 | FALSE | 31 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
56 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
56 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
56 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
56 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
56 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
56 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
56 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
56 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
56 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
56 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
56 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
56 | 3 | Pipes in the wall | Plumbing | 175 | FALSE | in_progress | 37 | 40 | 135 | FALSE | 40 | Partition phase 1 | 0 | 0 | TRUE | FALSE
56 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
56 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
56 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 185 | 0 | FALSE | FALSE
56 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
56 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
56 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
56 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
57 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
57 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
57 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
57 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
57 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
57 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
57 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
57 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
57 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
57 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
57 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
57 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
57 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
57 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
57 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 57 | 546 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
57 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
57 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
57 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
57 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
57 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
57 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
57 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
57 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
57 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
57 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
57 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
57 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
57 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 96 | 0 | FALSE | FALSE
57 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
57 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
57 | 1 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 30 | 155 | FALSE | 30 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
57 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
57 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
57 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
57 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
57 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
57 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
57 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
57 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
57 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
57 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
57 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
57 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 39 | 96 | FALSE | 39 | Partition phase 1 | 0 | 0 | TRUE | FALSE
57 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
57 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
57 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 155 | 0 | FALSE | FALSE
57 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
57 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
57 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
57 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
58 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
58 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
58 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
58 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
58 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
58 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
58 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
58 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
58 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
58 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
58 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
58 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
58 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
58 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
58 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 58 | 488 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
58 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
58 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
58 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
58 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
58 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
58 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
58 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
58 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
58 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
58 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
58 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
58 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
58 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 60 | 0 | FALSE | FALSE
58 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
58 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
58 | 1 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 33 | 122 | FALSE | 33 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
58 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
58 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
58 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
58 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
58 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
58 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
58 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
58 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
58 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
58 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
58 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
58 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 36 | 60 | FALSE | 36 | Partition phase 1 | 0 | 0 | TRUE | FALSE
58 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
58 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
58 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 122 | 0 | FALSE | FALSE
58 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
58 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
58 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
58 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
59 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
59 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
59 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
59 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
59 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
59 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
59 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
59 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
59 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
59 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
59 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
59 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
59 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
59 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
59 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 61 | 427 | FALSE | 61 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
59 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
59 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
59 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
59 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
59 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
59 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
59 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
59 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
59 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
59 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
59 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
59 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
59 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 27 | 0 | FALSE | FALSE
59 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
59 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
59 | 1 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 32 | 90 | FALSE | 32 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
59 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
59 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
59 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
59 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
59 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
59 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
59 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
59 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
59 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
59 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
59 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
59 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 33 | 27 | FALSE | 33 | Partition phase 1 | 0 | 0 | TRUE | FALSE
59 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
59 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
59 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 90 | 0 | FALSE | FALSE
59 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
59 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
59 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
59 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
60 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
60 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
60 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
60 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
60 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
60 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
60 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
60 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
60 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
60 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 66 | 361 | FALSE | 66 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
60 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
60 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
60 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
60 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
60 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
60 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
60 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
60 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
60 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
60 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
60 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
60 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
60 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
60 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
60 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
60 | 1 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 34 | 56 | FALSE | 34 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
60 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
60 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
60 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
60 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
60 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
60 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
60 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
60 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | 39 | 0 | FALSE | 27 | Partition phase 1 | 0 | 1 | TRUE | FALSE
60 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
60 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
60 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 56 | 0 | FALSE | FALSE
60 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
60 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
60 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
60 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
61 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
61 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
61 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
61 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
61 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
61 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
61 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
61 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
61 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
61 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 58 | 303 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
61 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
61 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
61 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
61 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
61 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
61 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
61 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
61 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
61 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
61 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
61 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
61 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
61 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
61 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
61 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
61 | 1 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 34 | 22 | FALSE | 34 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
61 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
61 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
61 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
61 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
61 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
61 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
61 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
61 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
61 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
61 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
61 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 22 | 0 | FALSE | FALSE
61 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
61 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
61 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
61 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
62 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
62 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
62 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
62 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
62 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
62 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
62 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
62 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
62 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
62 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 57 | 246 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
62 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
62 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
62 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
62 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
62 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
62 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
62 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
62 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
62 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
62 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
62 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
62 | 2 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | TRUE
62 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | TRUE
62 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
62 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
62 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | 30 | 0 | FALSE | 22 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
62 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
62 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
62 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
62 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
62 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
62 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
62 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
62 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
62 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
62 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
62 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
62 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
62 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
62 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
62 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
63 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
63 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | TRUE
63 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
63 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
63 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
63 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
63 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
63 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
63 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
63 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 59 | 187 | FALSE | 59 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
63 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
63 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
63 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
63 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
63 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
63 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
63 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
63 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
63 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
63 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
63 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
63 | 2 | Partition phase 2 | Partition | 19 | FALSE | completed | 51 | 19 | 0 | FALSE | 19 | Pipes in the wall | 0 | 1 | TRUE | FALSE
63 | 3 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | TRUE
63 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
63 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
63 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
63 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
63 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
63 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
63 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
63 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
63 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
63 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
63 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
63 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
63 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
63 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
63 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
63 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
63 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
63 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
64 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
64 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
64 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
64 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
64 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
64 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
64 | 2 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 44 | 120 | FALSE | 44 | Partition phase 2 | 0 | 0 | TRUE | FALSE
64 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
64 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
64 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
64 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
64 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
64 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
64 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
64 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 58 | 129 | FALSE | 58 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
64 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
64 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
64 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
64 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
64 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
64 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
64 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
64 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
64 | 4 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
64 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
64 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
64 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
64 | 3 | Partition phase 2 | Partition | 19 | FALSE | completed | 51 | 19 | 0 | FALSE | 19 | Pipes in the wall | 0 | 1 | TRUE | FALSE
64 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
64 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
64 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
64 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 120 | 1 | FALSE | FALSE
64 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
64 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
64 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
64 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
64 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
64 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
64 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
64 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
64 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
64 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
64 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
64 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
64 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
64 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
64 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
64 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
64 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
64 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
65 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
65 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
65 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
65 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
65 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
65 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
65 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 41 | 79 | FALSE | 41 | Partition phase 2 | 0 | 0 | TRUE | FALSE
65 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
65 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
65 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
65 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
65 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
65 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
65 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
65 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 57 | 72 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
65 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
65 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
65 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
65 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
65 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
65 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
65 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
65 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
65 | 4 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 51 | 767 | FALSE | 51 | null | null | 0 | TRUE | FALSE
65 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
65 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
65 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
65 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
65 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
65 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
65 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
65 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 79 | 0 | FALSE | FALSE
65 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
65 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
65 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
65 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
65 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
65 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
65 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
65 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
65 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
65 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
65 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
65 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 767 | 1 | FALSE | FALSE
65 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
65 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
65 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
65 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
65 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
65 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
66 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
66 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
66 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
66 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
66 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
66 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
66 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 38 | 41 | FALSE | 38 | Partition phase 2 | 0 | 0 | TRUE | FALSE
66 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
66 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
66 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
66 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
66 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
66 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
66 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
66 | 5 | Floor tiling | Tiling | 661 | TRUE | in_progress | 62 | 57 | 15 | FALSE | 57 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
66 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
66 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
66 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
66 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
66 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
66 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
66 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
66 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
66 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 58 | 709 | FALSE | 58 | null | null | 0 | TRUE | FALSE
66 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
66 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
66 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
66 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
66 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
66 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
66 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
66 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 41 | 0 | FALSE | FALSE
66 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
66 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
66 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
66 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
66 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
66 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
66 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
66 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
66 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
66 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
66 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
66 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 709 | 1 | FALSE | FALSE
66 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
66 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
66 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
66 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
66 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
66 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
67 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
67 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | 42 | 0 | FALSE | 41 | Partition phase 2 | 0 | 1 | TRUE | FALSE
67 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | TRUE
67 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
67 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
67 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
67 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
67 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
67 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
67 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | 64 | 0 | FALSE | 15 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
67 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
67 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
67 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
67 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
67 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
67 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
67 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
67 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
67 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 655 | FALSE | 54 | null | null | 0 | TRUE | FALSE
67 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
67 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
67 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
67 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
67 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
67 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
67 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
67 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
67 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
67 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
67 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
67 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
67 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
67 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
67 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
67 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 655 | 1 | FALSE | FALSE
67 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
67 | 1 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | TRUE
67 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
67 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
67 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
67 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
68 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
68 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
68 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
68 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
68 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
68 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
68 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
68 | 3 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 42 | 122 | FALSE | 42 | Partition phase 2 | 0 | 0 | TRUE | FALSE
68 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
68 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
68 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
68 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
68 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
68 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
68 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
68 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
68 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
68 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
68 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
68 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
68 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
68 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
68 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
68 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 56 | 599 | FALSE | 56 | null | null | 0 | TRUE | FALSE
68 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
68 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
68 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
68 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
68 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
68 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
68 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
68 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
68 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 122 | 0 | FALSE | FALSE
68 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
68 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
68 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
68 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
68 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
68 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
68 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
68 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
68 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
68 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
68 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 599 | 1 | FALSE | FALSE
68 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
68 | 1 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 29 | 242 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
68 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
68 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
68 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
68 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
69 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
69 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
69 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
69 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
69 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
69 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
69 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
69 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 37 | 85 | FALSE | 37 | Partition phase 2 | 0 | 0 | TRUE | FALSE
69 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
69 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
69 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
69 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
69 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
69 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
69 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
69 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
69 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
69 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
69 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
69 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
69 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
69 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
69 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
69 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 0 | 599 | TRUE | 0 | null | null | 0 | TRUE | FALSE
69 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
69 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
69 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
69 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
69 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
69 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
69 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
69 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
69 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 85 | 0 | FALSE | FALSE
69 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
69 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
69 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
69 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
69 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
69 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
69 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
69 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
69 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
69 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
69 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 599 | 1 | FALSE | FALSE
69 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
69 | 1 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 0 | 242 | TRUE | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
69 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
69 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
69 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
69 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
70 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
70 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
70 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
70 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
70 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
70 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
70 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
70 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 41 | 44 | FALSE | 41 | Partition phase 2 | 0 | 0 | TRUE | FALSE
70 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
70 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
70 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
70 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
70 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
70 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
70 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
70 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
70 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
70 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
70 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
70 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
70 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
70 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
70 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
70 | 4 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 52 | 547 | FALSE | 52 | null | null | 0 | TRUE | FALSE
70 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
70 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
70 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
70 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
70 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
70 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
70 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
70 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
70 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 44 | 0 | FALSE | FALSE
70 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
70 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
70 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
70 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
70 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
70 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
70 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
70 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
70 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
70 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
70 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 547 | 1 | FALSE | FALSE
70 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
70 | 1 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 27 | 215 | FALSE | 27 | Partition phase 3 | 0 | 0 | TRUE | FALSE
70 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
70 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
70 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
70 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
71 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
71 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
71 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
71 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
71 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
71 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
71 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
71 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 41 | 3 | FALSE | 41 | Partition phase 2 | 0 | 0 | TRUE | FALSE
71 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
71 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
71 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
71 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
71 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
71 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
71 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
71 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
71 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
71 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
71 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
71 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
71 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
71 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
71 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
71 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 57 | 490 | FALSE | 57 | null | null | 0 | TRUE | FALSE
71 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
71 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
71 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
71 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
71 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
71 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
71 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
71 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
71 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 3 | 0 | FALSE | FALSE
71 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
71 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
71 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
71 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
71 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
71 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
71 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
71 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
71 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
71 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
71 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 490 | 1 | FALSE | FALSE
71 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
71 | 1 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 29 | 186 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
71 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
71 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
71 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
71 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
72 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
72 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
72 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | 41 | 0 | FALSE | 3 | Partition phase 2 | 0 | 1 | TRUE | FALSE
72 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
72 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
72 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
72 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
72 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
72 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
72 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
72 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
72 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
72 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
72 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
72 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
72 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
72 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
72 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
72 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 52 | 438 | FALSE | 52 | null | null | 0 | TRUE | FALSE
72 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
72 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
72 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
72 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
72 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
72 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
72 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
72 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
72 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
72 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
72 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
72 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
72 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
72 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
72 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
72 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 438 | 1 | FALSE | FALSE
72 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
72 | 1 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 25 | 161 | FALSE | 25 | Partition phase 3 | 0 | 0 | TRUE | FALSE
72 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
72 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
72 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
72 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
73 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
73 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
73 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
73 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
73 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
73 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
73 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
73 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
73 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
73 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
73 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
73 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
73 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
73 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
73 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
73 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
73 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
73 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
73 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 60 | 378 | FALSE | 60 | null | null | 0 | TRUE | FALSE
73 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
73 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
73 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
73 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
73 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
73 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
73 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
73 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
73 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
73 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
73 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
73 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
73 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
73 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
73 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
73 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 378 | 1 | FALSE | FALSE
73 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
73 | 1 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 25 | 136 | FALSE | 25 | Partition phase 3 | 0 | 0 | TRUE | FALSE
73 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
73 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
73 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
73 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
74 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
74 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
74 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
74 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
74 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
74 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
74 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
74 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
74 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
74 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
74 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
74 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
74 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
74 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
74 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
74 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
74 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
74 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
74 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 52 | 326 | FALSE | 52 | null | null | 0 | TRUE | FALSE
74 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
74 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
74 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
74 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
74 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
74 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
74 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
74 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
74 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
74 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
74 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
74 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
74 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
74 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
74 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
74 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 326 | 1 | FALSE | FALSE
74 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
74 | 1 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 28 | 108 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
74 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
74 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
74 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
74 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
75 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
75 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
75 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
75 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
75 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
75 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
75 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
75 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
75 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
75 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
75 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
75 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
75 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
75 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
75 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
75 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
75 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
75 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
75 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 51 | 275 | FALSE | 51 | null | null | 0 | TRUE | FALSE
75 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
75 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
75 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
75 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
75 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
75 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
75 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
75 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
75 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
75 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
75 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
75 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
75 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
75 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
75 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
75 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 275 | 1 | FALSE | FALSE
75 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
75 | 1 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 30 | 78 | FALSE | 30 | Partition phase 3 | 0 | 0 | TRUE | FALSE
75 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
75 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
75 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
75 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
76 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
76 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
76 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
76 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
76 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
76 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
76 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
76 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
76 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
76 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
76 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
76 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
76 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
76 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
76 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
76 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
76 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
76 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
76 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 58 | 217 | FALSE | 58 | null | null | 0 | TRUE | FALSE
76 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
76 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
76 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
76 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
76 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
76 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
76 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
76 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
76 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
76 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
76 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
76 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
76 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
76 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
76 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
76 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 217 | 1 | FALSE | FALSE
76 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
76 | 1 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 29 | 49 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
76 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
76 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
76 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
76 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
77 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
77 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
77 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
77 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
77 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
77 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
77 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
77 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
77 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
77 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
77 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
77 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
77 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
77 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
77 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
77 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
77 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
77 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
77 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 163 | FALSE | 54 | null | null | 0 | TRUE | FALSE
77 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
77 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
77 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
77 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
77 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
77 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
77 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
77 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
77 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
77 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
77 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
77 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
77 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
77 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
77 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
77 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 163 | 1 | FALSE | FALSE
77 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
77 | 1 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 28 | 21 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
77 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
77 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
77 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
77 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
78 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
78 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
78 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
78 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
78 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
78 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
78 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
78 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
78 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
78 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
78 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
78 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
78 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
78 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
78 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
78 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
78 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
78 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
78 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 109 | FALSE | 54 | null | null | 0 | TRUE | FALSE
78 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
78 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
78 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
78 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
78 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
78 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
78 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
78 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
78 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
78 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
78 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
78 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
78 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
78 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
78 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
78 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 109 | 1 | FALSE | FALSE
78 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
78 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | 27 | 0 | FALSE | 21 | Partition phase 3 | 0 | 1 | TRUE | FALSE
78 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
78 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
78 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
78 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
79 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
79 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
79 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
79 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
79 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
79 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
79 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
79 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
79 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
79 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
79 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
79 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
79 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
79 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
79 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
79 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
79 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
79 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
79 | 4 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 57 | 52 | FALSE | 57 | null | null | 0 | TRUE | FALSE
79 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
79 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
79 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
79 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
79 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
79 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
79 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
79 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
79 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
79 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
79 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
79 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
79 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
79 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
79 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
79 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 52 | 1 | FALSE | FALSE
79 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
79 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
79 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
79 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
79 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
79 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
80 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
80 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
80 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
80 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
80 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
80 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
80 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
80 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
80 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
80 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
80 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
80 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
80 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
80 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
80 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
80 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
80 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
80 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
80 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | 55 | 0 | FALSE | 52 | null | null | 1 | TRUE | FALSE
80 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
80 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
80 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
80 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
80 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
80 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
80 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
80 | 2 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | TRUE
80 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | TRUE
80 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
80 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
80 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
80 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
80 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
80 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
80 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | TRUE
80 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
80 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
80 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
80 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
80 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
80 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
81 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
81 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
81 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
81 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
81 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
81 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
81 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
81 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
81 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
81 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
81 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
81 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
81 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
81 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
81 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
81 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
81 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
81 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
81 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
81 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
81 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
81 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
81 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
81 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
81 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
81 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
81 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
81 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
81 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 135 | 0 | FALSE | FALSE
81 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
81 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
81 | 2 | Partition phase 3 | Partition | 216 | FALSE | in_progress | 32 | 30 | 186 | FALSE | 30 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
81 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
81 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
81 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
81 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
81 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
81 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
81 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
81 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
81 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
81 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
81 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
81 | 4 | Pipes in the wall | Plumbing | 175 | FALSE | in_progress | 37 | 40 | 135 | FALSE | 40 | Partition phase 1 | 0 | 0 | TRUE | FALSE
81 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
81 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
81 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 186 | 1 | FALSE | FALSE
81 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
81 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
81 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
82 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
82 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
82 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
82 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
82 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
82 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
82 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
82 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
82 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
82 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
82 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
82 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
82 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
82 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
82 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
82 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
82 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
82 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
82 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
82 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
82 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
82 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
82 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
82 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
82 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
82 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
82 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
82 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
82 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 100 | 0 | FALSE | FALSE
82 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
82 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
82 | 2 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 33 | 153 | FALSE | 33 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
82 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
82 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
82 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
82 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
82 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
82 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
82 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
82 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
82 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
82 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
82 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
82 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 35 | 100 | FALSE | 35 | Partition phase 1 | 0 | 0 | TRUE | FALSE
82 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
82 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
82 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 153 | 1 | FALSE | FALSE
82 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
82 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
82 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
83 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
83 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
83 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
83 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
83 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
83 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
83 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
83 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
83 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
83 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
83 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
83 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
83 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
83 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
83 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
83 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
83 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
83 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
83 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
83 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
83 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
83 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
83 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
83 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
83 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
83 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
83 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
83 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
83 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 62 | 0 | FALSE | FALSE
83 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
83 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
83 | 2 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 29 | 124 | FALSE | 29 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
83 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
83 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
83 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
83 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
83 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
83 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
83 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
83 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
83 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
83 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
83 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
83 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 38 | 62 | FALSE | 38 | Partition phase 1 | 0 | 0 | TRUE | FALSE
83 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
83 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
83 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 124 | 1 | FALSE | FALSE
83 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
83 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
83 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
84 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
84 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
84 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
84 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
84 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
84 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
84 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
84 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
84 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
84 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
84 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
84 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
84 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
84 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
84 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
84 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
84 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
84 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
84 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
84 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
84 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
84 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
84 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
84 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
84 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
84 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
84 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
84 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
84 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 22 | 0 | FALSE | FALSE
84 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
84 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
84 | 2 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 32 | 92 | FALSE | 32 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
84 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
84 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
84 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
84 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
84 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
84 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
84 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
84 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
84 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
84 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
84 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
84 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 40 | 22 | FALSE | 40 | Partition phase 1 | 0 | 0 | TRUE | FALSE
84 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 0 | FALSE | FALSE
84 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
84 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 92 | 1 | FALSE | FALSE
84 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
84 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
84 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
85 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
85 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
85 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
85 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
85 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
85 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
85 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
85 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
85 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
85 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
85 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
85 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
85 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
85 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
85 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
85 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
85 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
85 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
85 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
85 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
85 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
85 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
85 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
85 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
85 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
85 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
85 | 2 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 29 | 63 | FALSE | 29 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
85 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
85 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
85 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
85 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
85 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
85 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
85 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
85 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | 34 | 0 | FALSE | 22 | Partition phase 1 | 0 | 1 | TRUE | FALSE
85 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
85 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
85 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 63 | 1 | FALSE | FALSE
85 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
85 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
85 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
86 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
86 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
86 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
86 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
86 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
86 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
86 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
86 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
86 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
86 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
86 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
86 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
86 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
86 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
86 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
86 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
86 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
86 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
86 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
86 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
86 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
86 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
86 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
86 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
86 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
86 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
86 | 2 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 33 | 30 | FALSE | 33 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
86 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
86 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
86 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
86 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
86 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
86 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
86 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
86 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
86 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
86 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
86 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 30 | 1 | FALSE | FALSE
86 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
86 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
86 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
87 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
87 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
87 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
87 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
87 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
87 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
87 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
87 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
87 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
87 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
87 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
87 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
87 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
87 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
87 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
87 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | TRUE
87 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
87 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
87 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | 35 | 0 | FALSE | 30 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
87 | 3 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | TRUE
87 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
87 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
87 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
87 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
87 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
87 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
87 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
87 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
87 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
87 | 2 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | TRUE
87 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
87 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
87 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
88 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
88 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
88 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
88 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
88 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
88 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
88 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
88 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
88 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
88 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
88 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
88 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
88 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
88 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
88 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
88 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
88 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
88 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
88 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
88 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
88 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
88 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
88 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
88 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
88 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
88 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
88 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
88 | 3 | Partition phase 3 | Partition | 216 | FALSE | in_progress | 32 | 32 | 184 | FALSE | 32 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
88 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
88 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
88 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
88 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
88 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
88 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
88 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
88 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
88 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
88 | 2 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 28 | 243 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
88 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 184 | 0 | FALSE | FALSE
88 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
88 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
89 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
89 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
89 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
89 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
89 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
89 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
89 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
89 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
89 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
89 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
89 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
89 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
89 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
89 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
89 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
89 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
89 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
89 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
89 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
89 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
89 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
89 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
89 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
89 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
89 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
89 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
89 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
89 | 3 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 29 | 155 | FALSE | 29 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
89 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
89 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
89 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
89 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
89 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
89 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
89 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
89 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
89 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
89 | 2 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 29 | 214 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
89 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 155 | 0 | FALSE | FALSE
89 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
89 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
90 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
90 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
90 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
90 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
90 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
90 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
90 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
90 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
90 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
90 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
90 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
90 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
90 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
90 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
90 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
90 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
90 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
90 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
90 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
90 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
90 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
90 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
90 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
90 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
90 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
90 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
90 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
90 | 3 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 29 | 126 | FALSE | 29 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
90 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
90 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
90 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
90 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
90 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
90 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
90 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
90 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
90 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
90 | 2 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 27 | 187 | FALSE | 27 | Partition phase 3 | 0 | 0 | TRUE | FALSE
90 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 126 | 0 | FALSE | FALSE
90 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
90 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
91 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
91 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
91 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
91 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
91 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
91 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
91 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
91 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
91 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
91 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
91 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
91 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
91 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
91 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
91 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
91 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
91 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
91 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
91 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
91 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
91 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
91 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
91 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
91 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
91 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
91 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
91 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
91 | 3 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 33 | 93 | FALSE | 33 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
91 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
91 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
91 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
91 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
91 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
91 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
91 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
91 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
91 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
91 | 2 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 28 | 159 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
91 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 93 | 0 | FALSE | FALSE
91 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
91 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
92 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
92 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
92 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
92 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
92 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
92 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
92 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
92 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
92 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
92 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
92 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
92 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
92 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
92 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
92 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
92 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
92 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
92 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
92 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
92 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
92 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
92 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
92 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
92 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
92 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
92 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
92 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
92 | 3 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 34 | 59 | FALSE | 34 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
92 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
92 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
92 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
92 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
92 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
92 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
92 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
92 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
92 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
92 | 2 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 26 | 133 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
92 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 59 | 0 | FALSE | FALSE
92 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
92 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
93 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
93 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
93 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
93 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
93 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
93 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
93 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
93 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
93 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
93 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
93 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
93 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
93 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
93 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
93 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
93 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
93 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
93 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
93 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
93 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 0 | TRUE | FALSE
93 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
93 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
93 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
93 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
93 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
93 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
93 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
93 | 3 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 33 | 26 | FALSE | 33 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
93 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
93 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
93 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
93 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
93 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
93 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
93 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
93 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
93 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
93 | 2 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 26 | 107 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
93 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 26 | 0 | FALSE | FALSE
93 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
93 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
94 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
94 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
94 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
94 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
94 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
94 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
94 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
94 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
94 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
94 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
94 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
94 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
94 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
94 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
94 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
94 | 4 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | TRUE
94 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
94 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
94 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
94 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | 34 | 0 | FALSE | 26 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
94 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
94 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
94 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
94 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
94 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
94 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
94 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
94 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
94 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
94 | 2 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 28 | 79 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
94 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
94 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
94 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
95 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
95 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
95 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
95 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | TRUE
95 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
95 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
95 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
95 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
95 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
95 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
95 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
95 | 5 | Partition phase 1 | Partition | 818 | FALSE | pending | 55 | null | 818 | null | 0 | null | null | 1 | TRUE | TRUE
95 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
95 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
95 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
95 | 4 | Partition phase 2 | Partition | 19 | FALSE | completed | 51 | 19 | 0 | FALSE | 19 | Pipes in the wall | 0 | 1 | TRUE | FALSE
95 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
95 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
95 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
95 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
95 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
95 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
95 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
95 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
95 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
95 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
95 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
95 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 818 | 1 | FALSE | FALSE
95 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
95 | 2 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 0 | 79 | TRUE | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
95 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
95 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
95 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
96 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
96 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
96 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
96 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
96 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
96 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
96 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
96 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
96 | 4 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 41 | 123 | FALSE | 41 | Partition phase 2 | 0 | 0 | TRUE | FALSE
96 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
96 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
96 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
96 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
96 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
96 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
96 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
96 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
96 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
96 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
96 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
96 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
96 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
96 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
96 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
96 | 5 | Partition phase 1 | Partition | 818 | FALSE | in_progress | 55 | 59 | 759 | FALSE | 59 | null | null | 0 | TRUE | FALSE
96 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
96 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
96 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
96 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
96 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
96 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
96 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
96 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
96 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 123 | 0 | FALSE | FALSE
96 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
96 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
96 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
96 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
96 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
96 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
96 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
96 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
96 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
96 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
96 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 759 | 1 | FALSE | FALSE
96 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
96 | 2 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 28 | 51 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
96 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
96 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
96 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
97 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
97 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
97 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
97 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
97 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
97 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
97 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
97 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
97 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 40 | 83 | FALSE | 40 | Partition phase 2 | 0 | 0 | TRUE | FALSE
97 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
97 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
97 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
97 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
97 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
97 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
97 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
97 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
97 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
97 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
97 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
97 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
97 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
97 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
97 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
97 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 56 | 703 | FALSE | 56 | null | null | 0 | TRUE | FALSE
97 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
97 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
97 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
97 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
97 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
97 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
97 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
97 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
97 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 83 | 0 | FALSE | FALSE
97 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
97 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
97 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
97 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
97 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
97 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
97 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
97 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
97 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
97 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
97 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 703 | 1 | FALSE | FALSE
97 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
97 | 2 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 28 | 23 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
97 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
97 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
97 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
98 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
98 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
98 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
98 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
98 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
98 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
98 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
98 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
98 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 41 | 42 | FALSE | 41 | Partition phase 2 | 0 | 0 | TRUE | FALSE
98 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 0 | FALSE | FALSE
98 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
98 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
98 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
98 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
98 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
98 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
98 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
98 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
98 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
98 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
98 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
98 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
98 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
98 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
98 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 56 | 647 | FALSE | 56 | null | null | 0 | TRUE | FALSE
98 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
98 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
98 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
98 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
98 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
98 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
98 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
98 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
98 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 42 | 0 | FALSE | FALSE
98 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
98 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
98 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
98 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
98 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
98 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
98 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
98 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
98 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
98 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
98 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 647 | 1 | FALSE | FALSE
98 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
98 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | 26 | 0 | FALSE | 23 | Partition phase 3 | 0 | 1 | TRUE | FALSE
98 | 3 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | TRUE
98 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
98 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
99 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
99 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
99 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
99 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | 43 | 0 | FALSE | 42 | Partition phase 2 | 0 | 1 | TRUE | FALSE
99 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
99 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
99 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
99 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
99 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
99 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
99 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
99 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
99 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
99 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
99 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
99 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
99 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
99 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
99 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
99 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 58 | 589 | FALSE | 58 | null | null | 0 | TRUE | FALSE
99 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
99 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
99 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
99 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
99 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
99 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
99 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
99 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
99 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
99 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
99 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
99 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
99 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
99 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
99 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
99 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 589 | 1 | FALSE | FALSE
99 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
99 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
99 | 3 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 0 | 271 | TRUE | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
99 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
99 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
100 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
100 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
100 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
100 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
100 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
100 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
100 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
100 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
100 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
100 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
100 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
100 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
100 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
100 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
100 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
100 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
100 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
100 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
100 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
100 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 60 | 529 | FALSE | 60 | null | null | 0 | TRUE | FALSE
100 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
100 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
100 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
100 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
100 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
100 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
100 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
100 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
100 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
100 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
100 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
100 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
100 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
100 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
100 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
100 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 529 | 1 | FALSE | FALSE
100 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
100 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
100 | 3 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 24 | 247 | FALSE | 24 | Partition phase 3 | 0 | 0 | TRUE | FALSE
100 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
100 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
101 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
101 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
101 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
101 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
101 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
101 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
101 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
101 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
101 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
101 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
101 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
101 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
101 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
101 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
101 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
101 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
101 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
101 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
101 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
101 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 53 | 476 | FALSE | 53 | null | null | 0 | TRUE | FALSE
101 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
101 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
101 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
101 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
101 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
101 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
101 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
101 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
101 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
101 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
101 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
101 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
101 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
101 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
101 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
101 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 476 | 1 | FALSE | FALSE
101 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
101 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
101 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 28 | 219 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
101 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
101 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
102 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
102 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
102 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
102 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
102 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
102 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
102 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
102 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
102 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
102 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
102 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
102 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
102 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
102 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
102 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
102 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
102 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
102 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
102 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
102 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 59 | 417 | FALSE | 59 | null | null | 0 | TRUE | FALSE
102 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
102 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
102 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
102 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
102 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
102 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
102 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
102 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
102 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
102 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
102 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
102 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
102 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
102 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
102 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
102 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 417 | 1 | FALSE | FALSE
102 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
102 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
102 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 27 | 192 | FALSE | 27 | Partition phase 3 | 0 | 0 | TRUE | FALSE
102 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
102 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
103 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
103 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
103 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
103 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
103 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
103 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
103 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
103 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
103 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
103 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
103 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
103 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
103 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
103 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
103 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
103 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
103 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
103 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
103 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
103 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 363 | FALSE | 54 | null | null | 0 | TRUE | FALSE
103 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
103 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
103 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
103 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
103 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
103 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
103 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
103 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
103 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
103 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
103 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
103 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
103 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
103 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
103 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
103 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 363 | 1 | FALSE | FALSE
103 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
103 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
103 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 29 | 163 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
103 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
103 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
104 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
104 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
104 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
104 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
104 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
104 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
104 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
104 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
104 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
104 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
104 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
104 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
104 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
104 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
104 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
104 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
104 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
104 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
104 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
104 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 55 | 308 | FALSE | 55 | null | null | 0 | TRUE | FALSE
104 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
104 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
104 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
104 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
104 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
104 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
104 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
104 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
104 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
104 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
104 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
104 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
104 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
104 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
104 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
104 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 308 | 1 | FALSE | FALSE
104 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
104 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
104 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 26 | 137 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
104 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
104 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
105 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
105 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
105 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
105 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
105 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
105 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
105 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
105 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
105 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
105 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
105 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
105 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
105 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
105 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
105 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
105 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
105 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
105 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
105 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
105 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 59 | 249 | FALSE | 59 | null | null | 0 | TRUE | FALSE
105 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
105 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
105 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
105 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
105 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
105 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
105 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
105 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
105 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
105 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
105 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
105 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
105 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
105 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
105 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
105 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 249 | 1 | FALSE | FALSE
105 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
105 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
105 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 0 | 137 | TRUE | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
105 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
105 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
106 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
106 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
106 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
106 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
106 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
106 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
106 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
106 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
106 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
106 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
106 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
106 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
106 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
106 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
106 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
106 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
106 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
106 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
106 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
106 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 55 | 194 | FALSE | 55 | null | null | 0 | TRUE | FALSE
106 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
106 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
106 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
106 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
106 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
106 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
106 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
106 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
106 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
106 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
106 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
106 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
106 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
106 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
106 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
106 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 194 | 1 | FALSE | FALSE
106 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
106 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
106 | 3 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 26 | 111 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
106 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
106 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
107 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
107 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
107 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
107 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
107 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
107 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
107 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
107 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
107 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
107 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
107 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
107 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
107 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
107 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
107 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
107 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
107 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
107 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
107 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
107 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 54 | 140 | FALSE | 54 | null | null | 0 | TRUE | FALSE
107 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
107 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
107 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
107 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
107 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
107 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
107 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
107 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
107 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
107 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
107 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
107 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
107 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
107 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
107 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
107 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 140 | 1 | FALSE | FALSE
107 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
107 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
107 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 26 | 85 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
107 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
107 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
108 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
108 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
108 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
108 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
108 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
108 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
108 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
108 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
108 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
108 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
108 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
108 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
108 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
108 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
108 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
108 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
108 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
108 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
108 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
108 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 59 | 81 | FALSE | 59 | null | null | 0 | TRUE | FALSE
108 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
108 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
108 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
108 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
108 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
108 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
108 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
108 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
108 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
108 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
108 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
108 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
108 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
108 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
108 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
108 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 81 | 1 | FALSE | FALSE
108 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
108 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
108 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 28 | 57 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
108 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
108 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
109 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
109 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
109 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
109 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
109 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
109 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
109 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
109 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
109 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
109 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
109 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
109 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
109 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
109 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
109 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
109 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
109 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
109 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
109 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
109 | 5 | Partition phase 1 | Partition | 818 | TRUE | in_progress | 55 | 53 | 28 | FALSE | 53 | null | null | 0 | TRUE | FALSE
109 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
109 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
109 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
109 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
109 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0 | FALSE | FALSE
109 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
109 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
109 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
109 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
109 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
109 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
109 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
109 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
109 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
109 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
109 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 28 | 1 | FALSE | FALSE
109 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
109 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
109 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 28 | 29 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
109 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
109 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
110 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
110 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
110 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
110 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
110 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
110 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
110 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
110 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
110 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
110 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
110 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
110 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | 57 | 0 | FALSE | 28 | null | null | 1 | TRUE | FALSE
110 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
110 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
110 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
110 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
110 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 1 | FALSE | FALSE
110 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
110 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
110 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
110 | 4 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | TRUE
110 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
110 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
110 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
110 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
110 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
110 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
110 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | TRUE
110 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
110 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
110 | 3 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 26 | 3 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
110 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
110 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
111 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
111 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
111 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
111 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
111 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
111 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
111 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
111 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
111 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
111 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
111 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
111 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
111 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
111 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
111 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
111 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
111 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
111 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
111 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
111 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
111 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
111 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
111 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
111 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
111 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
111 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
111 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
111 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
111 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
111 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 137 | 0 | FALSE | FALSE
111 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
111 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
111 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
111 | 4 | Partition phase 3 | Partition | 216 | FALSE | in_progress | 32 | 35 | 181 | FALSE | 35 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
111 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
111 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
111 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
111 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
111 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
111 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
111 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
111 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
111 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
111 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
111 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | in_progress | 37 | 38 | 137 | FALSE | 38 | Partition phase 1 | 0 | 0 | TRUE | FALSE
111 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
111 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
111 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | 27 | 0 | FALSE | 3 | Partition phase 3 | 0 | 1 | TRUE | FALSE
111 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 181 | 1 | FALSE | FALSE
111 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
112 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
112 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
112 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
112 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
112 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
112 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
112 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
112 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
112 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
112 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
112 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
112 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
112 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
112 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
112 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
112 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
112 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
112 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
112 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
112 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
112 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
112 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
112 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
112 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
112 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
112 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
112 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
112 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
112 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
112 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 137 | 0 | FALSE | FALSE
112 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
112 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
112 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
112 | 4 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 30 | 151 | FALSE | 30 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
112 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
112 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
112 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
112 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
112 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
112 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
112 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
112 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
112 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
112 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
112 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 0 | 137 | TRUE | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
112 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
112 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
112 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
112 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 151 | 1 | FALSE | FALSE
112 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
113 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
113 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
113 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
113 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
113 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
113 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
113 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
113 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
113 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
113 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
113 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
113 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
113 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
113 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
113 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
113 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
113 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
113 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
113 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
113 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
113 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
113 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
113 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
113 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
113 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
113 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
113 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
113 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
113 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
113 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 98 | 0 | FALSE | FALSE
113 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
113 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
113 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
113 | 4 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 35 | 116 | FALSE | 35 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
113 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
113 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
113 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
113 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
113 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
113 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
113 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
113 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
113 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
113 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
113 | 5 | Pipes in the wall | Plumbing | 175 | FALSE | in_progress | 37 | 39 | 98 | FALSE | 39 | Partition phase 1 | 0 | 0 | TRUE | FALSE
113 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
113 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
113 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
113 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 116 | 1 | FALSE | FALSE
113 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
114 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
114 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
114 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
114 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
114 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
114 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
114 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
114 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
114 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
114 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
114 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
114 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
114 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
114 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
114 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
114 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
114 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
114 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
114 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
114 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
114 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
114 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
114 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
114 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
114 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
114 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
114 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
114 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
114 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
114 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 64 | 0 | FALSE | FALSE
114 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
114 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
114 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
114 | 4 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 32 | 84 | FALSE | 32 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
114 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
114 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
114 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
114 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
114 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
114 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
114 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
114 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
114 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
114 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
114 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 34 | 64 | FALSE | 34 | Partition phase 1 | 0 | 0 | TRUE | FALSE
114 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
114 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
114 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
114 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 84 | 1 | FALSE | FALSE
114 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
115 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
115 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
115 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
115 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
115 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
115 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
115 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
115 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
115 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
115 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
115 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
115 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
115 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
115 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
115 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
115 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
115 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
115 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
115 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
115 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
115 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
115 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
115 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
115 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
115 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
115 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
115 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
115 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
115 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
115 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 26 | 0 | FALSE | FALSE
115 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
115 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
115 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
115 | 4 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 35 | 49 | FALSE | 35 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
115 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
115 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
115 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
115 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
115 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
115 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
115 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
115 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
115 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
115 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 0 | TRUE | FALSE
115 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | in_progress | 37 | 38 | 26 | FALSE | 38 | Partition phase 1 | 0 | 0 | TRUE | FALSE
115 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
115 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
115 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
115 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 49 | 1 | FALSE | FALSE
115 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
116 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
116 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
116 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
116 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
116 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
116 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
116 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
116 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
116 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
116 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
116 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
116 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
116 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
116 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
116 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
116 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
116 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
116 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
116 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
116 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
116 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
116 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
116 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
116 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
116 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
116 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
116 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
116 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
116 | 4 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 32 | 17 | FALSE | 32 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
116 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0 | FALSE | FALSE
116 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
116 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
116 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
116 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
116 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
116 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | 35 | 0 | FALSE | 26 | Partition phase 1 | 0 | 1 | TRUE | FALSE
116 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
116 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
116 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
116 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 17 | 1 | FALSE | FALSE
116 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
117 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
117 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
117 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
117 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
117 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1 | FALSE | FALSE
117 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
117 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
117 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
117 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
117 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
117 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
117 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
117 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
117 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
117 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
117 | 5 | Partition phase 2 | Partition | 19 | FALSE | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | TRUE
117 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
117 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
117 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
117 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | 31 | 0 | FALSE | 17 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
117 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
117 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
117 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
117 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
117 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
117 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
117 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
117 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
117 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
117 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
117 | 4 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | TRUE
117 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1 | FALSE | FALSE
118 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
118 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
118 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
118 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
118 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | TRUE
118 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
118 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
118 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
118 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
118 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
118 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
118 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
118 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
118 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
118 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
118 | 5 | Partition phase 2 | Partition | 19 | FALSE | completed | 51 | 19 | 0 | FALSE | 19 | Pipes in the wall | 0 | 1 | TRUE | FALSE
118 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
118 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
118 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
118 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
118 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
118 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
118 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
118 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
118 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
118 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
118 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
118 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
118 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
118 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
118 | 4 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 0 | 271 | TRUE | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
118 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
119 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
119 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
119 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
119 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
119 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
119 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
119 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
119 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
119 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
119 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 0 | 164 | TRUE | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
119 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
119 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
119 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
119 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
119 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
119 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
119 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
119 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
119 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
119 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
119 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
119 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
119 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
119 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
119 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
119 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
119 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
119 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
119 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
119 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
119 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
119 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
119 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
119 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
119 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
119 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
119 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
119 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
119 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
119 | 4 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 0 | 271 | TRUE | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
119 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
120 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
120 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
120 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
120 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
120 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
120 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
120 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
120 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
120 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
120 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 40 | 124 | FALSE | 40 | Partition phase 2 | 0 | 0 | TRUE | FALSE
120 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
120 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
120 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
120 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
120 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
120 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
120 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
120 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
120 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
120 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
120 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
120 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
120 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
120 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
120 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
120 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 124 | 1 | FALSE | FALSE
120 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
120 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
120 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
120 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
120 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
120 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
120 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
120 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
120 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
120 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
120 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
120 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
120 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
120 | 4 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 28 | 243 | FALSE | 28 | Partition phase 3 | 0 | 0 | TRUE | FALSE
120 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
121 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
121 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
121 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
121 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
121 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
121 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
121 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
121 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
121 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
121 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 43 | 81 | FALSE | 43 | Partition phase 2 | 0 | 0 | TRUE | FALSE
121 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
121 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
121 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
121 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
121 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
121 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
121 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
121 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
121 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
121 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
121 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
121 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
121 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
121 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
121 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
121 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 81 | 1 | FALSE | FALSE
121 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
121 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
121 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
121 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
121 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
121 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
121 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
121 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
121 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
121 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
121 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
121 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
121 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
121 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 26 | 217 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
121 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
122 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
122 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
122 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
122 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
122 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
122 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
122 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
122 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
122 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
122 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 0 | 81 | TRUE | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
122 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
122 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
122 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
122 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
122 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
122 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
122 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
122 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
122 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
122 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
122 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
122 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
122 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
122 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
122 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
122 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 81 | 1 | FALSE | FALSE
122 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
122 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
122 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
122 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
122 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
122 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
122 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
122 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
122 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
122 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
122 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
122 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
122 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
122 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 26 | 191 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
122 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
123 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
123 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
123 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
123 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
123 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
123 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
123 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
123 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
123 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
123 | 5 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 39 | 42 | FALSE | 39 | Partition phase 2 | 0 | 0 | TRUE | FALSE
123 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
123 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
123 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
123 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
123 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
123 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
123 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
123 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
123 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
123 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
123 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
123 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
123 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
123 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
123 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
123 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 42 | 1 | FALSE | FALSE
123 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
123 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
123 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
123 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
123 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
123 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
123 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
123 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
123 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
123 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
123 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
123 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
123 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
123 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 24 | 167 | FALSE | 24 | Partition phase 3 | 0 | 0 | TRUE | FALSE
123 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
124 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
124 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
124 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
124 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
124 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 0 | TRUE | FALSE
124 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
124 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
124 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
124 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
124 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 39 | 3 | FALSE | 39 | Partition phase 2 | 0 | 0 | TRUE | FALSE
124 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
124 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
124 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
124 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
124 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
124 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
124 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
124 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
124 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
124 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
124 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
124 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
124 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
124 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
124 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
124 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 3 | 1 | FALSE | FALSE
124 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
124 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
124 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
124 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
124 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
124 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
124 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
124 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
124 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
124 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
124 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
124 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
124 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
124 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 27 | 140 | FALSE | 27 | Partition phase 3 | 0 | 0 | TRUE | FALSE
124 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
125 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
125 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
125 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
125 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
125 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | 37 | 0 | FALSE | 3 | Partition phase 2 | 0 | 1 | TRUE | FALSE
125 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
125 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
125 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
125 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
125 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
125 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
125 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
125 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
125 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
125 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
125 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
125 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
125 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
125 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
125 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
125 | 5 | Partition phase 3 | Partition | 216 | FALSE | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | TRUE
125 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
125 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
125 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
125 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
125 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
125 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
125 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
125 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
125 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
125 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 29 | 111 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
125 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 0 | FALSE | FALSE
126 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
126 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
126 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
126 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
126 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
126 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
126 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
126 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
126 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
126 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
126 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
126 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
126 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
126 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
126 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
126 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
126 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
126 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
126 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
126 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
126 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
126 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
126 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
126 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
126 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
126 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
126 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
126 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
126 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
126 | 5 | Partition phase 3 | Partition | 216 | FALSE | in_progress | 32 | 35 | 181 | FALSE | 35 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
126 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
126 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
126 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
126 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
126 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
126 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
126 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
126 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
126 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
126 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 29 | 82 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
126 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 181 | 0 | FALSE | FALSE
127 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
127 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
127 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
127 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
127 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
127 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
127 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
127 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
127 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
127 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
127 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
127 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
127 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
127 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
127 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
127 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
127 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
127 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
127 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
127 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
127 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
127 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
127 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
127 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
127 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
127 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
127 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
127 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
127 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
127 | 5 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 29 | 152 | FALSE | 29 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
127 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
127 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
127 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
127 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
127 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
127 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
127 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
127 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
127 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
127 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 27 | 55 | FALSE | 27 | Partition phase 3 | 0 | 0 | TRUE | FALSE
127 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 152 | 0 | FALSE | FALSE
128 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
128 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
128 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
128 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
128 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
128 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
128 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
128 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
128 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
128 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
128 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
128 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
128 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
128 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
128 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
128 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
128 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
128 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
128 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
128 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
128 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
128 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
128 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
128 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
128 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
128 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
128 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
128 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
128 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
128 | 5 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 29 | 123 | FALSE | 29 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
128 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
128 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
128 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
128 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
128 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
128 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
128 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
128 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
128 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
128 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 25 | 30 | FALSE | 25 | Partition phase 3 | 0 | 0 | TRUE | FALSE
128 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 123 | 0 | FALSE | FALSE
129 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
129 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
129 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
129 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
129 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
129 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
129 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
129 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
129 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
129 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
129 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
129 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
129 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
129 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
129 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
129 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
129 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
129 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
129 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
129 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
129 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
129 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
129 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
129 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
129 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
129 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
129 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
129 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
129 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
129 | 5 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 32 | 91 | FALSE | 32 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
129 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
129 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
129 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
129 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
129 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
129 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
129 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
129 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
129 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
129 | 4 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 25 | 5 | FALSE | 25 | Partition phase 3 | 0 | 0 | TRUE | FALSE
129 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 91 | 0 | FALSE | FALSE
130 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
130 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
130 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
130 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
130 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
130 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
130 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
130 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
130 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
130 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
130 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
130 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
130 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
130 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
130 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
130 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
130 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
130 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
130 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
130 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
130 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
130 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
130 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
130 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
130 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
130 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
130 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
130 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
130 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
130 | 5 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 31 | 60 | FALSE | 31 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
130 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
130 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
130 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
130 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
130 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
130 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
130 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
130 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
130 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
130 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | 27 | 0 | FALSE | 5 | Partition phase 3 | 0 | 1 | TRUE | FALSE
130 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 60 | 1 | FALSE | FALSE
131 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
131 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
131 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
131 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
131 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
131 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
131 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
131 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
131 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
131 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
131 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
131 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
131 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
131 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
131 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
131 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
131 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
131 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
131 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
131 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 0 | TRUE | FALSE
131 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
131 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
131 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
131 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
131 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 0 | TRUE | FALSE
131 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
131 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
131 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
131 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
131 | 5 | Partition phase 3 | Partition | 216 | TRUE | in_progress | 32 | 35 | 25 | FALSE | 35 | Electric conduits in the wall | 0 | 0 | TRUE | FALSE
131 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
131 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
131 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
131 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
131 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
131 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
131 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
131 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
131 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
131 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
131 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 25 | 1 | FALSE | FALSE
132 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
132 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
132 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
132 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
132 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
132 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
132 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
132 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
132 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
132 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
132 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
132 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
132 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
132 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
132 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
132 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
132 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
132 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
132 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
132 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
132 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | 31 | 0 | FALSE | 25 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
132 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
132 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
132 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
132 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
132 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
132 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
132 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
132 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
132 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
132 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
132 | 5 | Wall tiling | Tiling | 271 | FALSE | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | TRUE
133 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
133 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
133 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
133 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
133 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
133 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
133 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
133 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
133 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
133 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
133 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
133 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
133 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
133 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
133 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
133 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
133 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
133 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
133 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
133 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
133 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
133 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
133 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
133 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
133 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
133 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
133 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
133 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
133 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
133 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
133 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
133 | 5 | Wall tiling | Tiling | 271 | FALSE | in_progress | 27 | 26 | 245 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
134 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
134 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
134 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
134 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
134 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
134 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
134 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
134 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
134 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
134 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
134 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
134 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
134 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
134 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
134 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
134 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
134 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
134 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
134 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
134 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
134 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
134 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
134 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
134 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
134 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
134 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
134 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
134 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
134 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
134 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
134 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
134 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 25 | 220 | FALSE | 25 | Partition phase 3 | 0 | 0 | TRUE | FALSE
135 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
135 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
135 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
135 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
135 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
135 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
135 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
135 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
135 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
135 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
135 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
135 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
135 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
135 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
135 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
135 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
135 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
135 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
135 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
135 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
135 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
135 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
135 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
135 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
135 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
135 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
135 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
135 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
135 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
135 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
135 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
135 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 25 | 195 | FALSE | 25 | Partition phase 3 | 0 | 0 | TRUE | FALSE
136 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
136 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
136 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
136 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
136 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
136 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
136 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
136 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
136 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
136 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
136 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
136 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
136 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
136 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
136 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
136 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
136 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
136 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
136 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
136 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
136 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
136 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
136 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
136 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
136 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
136 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
136 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
136 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
136 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
136 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
136 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
136 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 26 | 169 | FALSE | 26 | Partition phase 3 | 0 | 0 | TRUE | FALSE
137 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
137 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
137 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
137 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
137 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
137 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
137 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
137 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
137 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
137 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
137 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
137 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
137 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
137 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
137 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
137 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
137 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
137 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
137 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
137 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
137 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
137 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
137 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
137 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
137 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
137 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
137 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
137 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
137 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
137 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
137 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
137 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 30 | 139 | FALSE | 30 | Partition phase 3 | 0 | 0 | TRUE | FALSE
138 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
138 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
138 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
138 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
138 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
138 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
138 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
138 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
138 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
138 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
138 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
138 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
138 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
138 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
138 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
138 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
138 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
138 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
138 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
138 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
138 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
138 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
138 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
138 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
138 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
138 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
138 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
138 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
138 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
138 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
138 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
138 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 27 | 112 | FALSE | 27 | Partition phase 3 | 0 | 0 | TRUE | FALSE
139 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
139 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
139 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
139 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
139 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
139 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
139 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
139 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
139 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
139 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
139 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
139 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
139 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
139 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
139 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
139 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
139 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
139 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
139 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
139 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
139 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
139 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
139 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
139 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
139 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
139 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
139 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
139 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
139 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
139 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
139 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
139 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 27 | 85 | FALSE | 27 | Partition phase 3 | 0 | 0 | TRUE | FALSE
140 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
140 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
140 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
140 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
140 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
140 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
140 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
140 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
140 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
140 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
140 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
140 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
140 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
140 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
140 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
140 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
140 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
140 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
140 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
140 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
140 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
140 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
140 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
140 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
140 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
140 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
140 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
140 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
140 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
140 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
140 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
140 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 29 | 56 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
141 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
141 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
141 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
141 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
141 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
141 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
141 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
141 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
141 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
141 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
141 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
141 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
141 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
141 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
141 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
141 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
141 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
141 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
141 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
141 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
141 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
141 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
141 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
141 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
141 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
141 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
141 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
141 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
141 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
141 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
141 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
141 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 29 | 27 | FALSE | 29 | Partition phase 3 | 0 | 0 | TRUE | FALSE
142 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
142 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
142 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
142 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
142 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
142 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
142 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
142 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
142 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
142 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 0 | TRUE | FALSE
142 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
142 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
142 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
142 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
142 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
142 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
142 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
142 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
142 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
142 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
142 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
142 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
142 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
142 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
142 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
142 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
142 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
142 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
142 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
142 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
142 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 0 | TRUE | FALSE
142 | 5 | Wall tiling | Tiling | 271 | TRUE | in_progress | 27 | 25 | 2 | FALSE | 25 | Partition phase 3 | 0 | 0 | TRUE | FALSE
143 | 1 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 2 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 3 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 4 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 5 | Electric conduits in the floor | Electricity | 74 | TRUE | completed | 51 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
143 | 2 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
143 | 3 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
143 | 4 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
143 | 5 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | null | 0 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | FALSE
143 | 1 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
143 | 2 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
143 | 3 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
143 | 4 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
143 | 5 | Floor tiling | Tiling | 661 | TRUE | completed | 62 | null | 0 | null | 0 | Pipes in the floor, Electric conduits in the floor | 0, 0 | 1 | TRUE | FALSE
143 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 2 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 3 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 4 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 5 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 1 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 2 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 3 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 4 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 5 | Partition phase 1 | Partition | 818 | TRUE | completed | 55 | null | 0 | null | 0 | null | null | 1 | TRUE | FALSE
143 | 1 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
143 | 2 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
143 | 3 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
143 | 4 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
143 | 5 | Partition phase 2 | Partition | 19 | TRUE | completed | 51 | null | 0 | null | 0 | Pipes in the wall | 0 | 1 | TRUE | FALSE
143 | 1 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
143 | 2 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
143 | 3 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
143 | 4 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
143 | 5 | Partition phase 3 | Partition | 216 | TRUE | completed | 32 | null | 0 | null | 0 | Electric conduits in the wall | 0 | 1 | TRUE | FALSE
143 | 1 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 2 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 3 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 4 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 5 | Pipes in the floor | Plumbing | 103 | TRUE | completed | 69 | null | 0 | null | 0 | Gravel base layer | 0 | 1 | TRUE | FALSE
143 | 1 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
143 | 2 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
143 | 3 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
143 | 4 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
143 | 5 | Pipes in the wall | Plumbing | 175 | TRUE | completed | 37 | null | 0 | null | 0 | Partition phase 1 | 0 | 1 | TRUE | FALSE
143 | 1 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
143 | 2 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
143 | 3 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
143 | 4 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | null | 0 | null | 0 | Partition phase 3 | 0 | 1 | TRUE | FALSE
143 | 5 | Wall tiling | Tiling | 271 | TRUE | completed | 27 | 27 | 0 | FALSE | 2 | Partition phase 3 | 0 | 1 | TRUE | FALSE

## 数据初始化
day_number | floor | process | assigned_trade | planned_remaining | task_status | initial_production_rate | remain_work | predecessor_processes | pre_remain_work | trade_available | prerequisites_completed | can_start
0 | 1 | Electric conduits in the floor | Electricity | 74 | pending | 51 | 74 | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 1 | Electric conduits in the wall | Electricity | 164 | pending | 41 | 164 | Partition phase 2 | 19 | 1 | FALSE | FALSE
0 | 1 | Floor tiling | Tiling | 661 | pending | 62 | 661 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1 | FALSE | FALSE
0 | 1 | Gravel base layer | Gravel | 154 | pending | 34 | 154 | null | null | 1 | TRUE | TRUE
0 | 1 | Partition phase 1 | Partition | 818 | pending | 55 | 818 | null | null | 1 | TRUE | TRUE
0 | 1 | Partition phase 2 | Partition | 19 | pending | 51 | 19 | Pipes in the wall | 175 | 1 | FALSE | FALSE
0 | 1 | Partition phase 3 | Partition | 216 | pending | 32 | 216 | Electric conduits in the wall | 164 | 1 | FALSE | FALSE
0 | 1 | Pipes in the floor | Plumbing | 103 | pending | 69 | 103 | Gravel base layer | 154 | 1 | FALSE | FALSE
0 | 1 | Pipes in the wall | Plumbing | 175 | pending | 37 | 175 | Partition phase 1 | 818 | 1 | FALSE | FALSE
0 | 1 | Wall tiling | Tiling | 271 | pending | 27 | 271 | Partition phase 3 | 216 | 1 | FALSE | FALSE

## 第一天计算
day_number | floor | process | assigned_trade | planned_remaining | task_status | initial_production_rate | actual_efficiency | remain_work | is_rework | today_workload | predecessor_processes | pre_remain_work | trade_available
0 | 1 | Electric conduits in the floor | Electricity | 74 | pending | 51 | null | 74 | null | null | Gravel base layer | 154 | 1
0 | 1 | Electric conduits in the wall | Electricity | 164 | pending | 41 | null | 164 | null | null | Partition phase 2 | 19 | 1
0 | 1 | Floor tiling | Tiling | 661 | pending | 62 | null | 661 | null | null | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1
0 | 1 | Gravel base layer | Gravel | 154 | pending | 34 | null | 154 | null | null | null | null | 1
0 | 1 | Partition phase 1 | Partition | 818 | pending | 55 | null | 818 | null | null | null | null | 1
0 | 1 | Partition phase 2 | Partition | 19 | pending | 51 | null | 19 | null | null | Pipes in the wall | 175 | 1
0 | 1 | Partition phase 3 | Partition | 216 | pending | 32 | null | 216 | null | null | Electric conduits in the wall | 164 | 1
0 | 1 | Pipes in the floor | Plumbing | 103 | pending | 69 | null | 103 | null | null | Gravel base layer | 154 | 1
0 | 1 | Pipes in the wall | Plumbing | 175 | pending | 37 | null | 175 | null | null | Partition phase 1 | 818 | 1
0 | 1 | Wall tiling | Tiling | 271 | pending | 27 | null | 271 | null | null | Partition phase 3 | 216 | 1
1 | 1 | Electric conduits in the floor | Electricity | 74 | pending | 51 | null | 74 | null | 0 | Gravel base layer | 122 | 1
1 | 1 | Electric conduits in the wall | Electricity | 164 | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 19 | 1
1 | 1 | Floor tiling | Tiling | 661 | pending | 62 | null | 661 | null | 0 | Pipes in the floor, Electric conduits in the floor | 74, 103 | 1
1 | 1 | Gravel base layer | Gravel | 154 | in_progress | 34 | 32 | 122 | FALSE | 32 | null | null | 0
1 | 1 | Partition phase 1 | Partition | 818 | in_progress | 55 | 58 | 760 | FALSE | 58 | null | null | 0
1 | 1 | Partition phase 2 | Partition | 19 | pending | 51 | null | 19 | null | 0 | Pipes in the wall | 175 | 0
1 | 1 | Partition phase 3 | Partition | 216 | pending | 32 | null | 216 | null | 0 | Electric conduits in the wall | 164 | 0
1 | 1 | Pipes in the floor | Plumbing | 103 | pending | 69 | null | 103 | null | 0 | Gravel base layer | 122 | 1
1 | 1 | Pipes in the wall | Plumbing | 175 | pending | 37 | null | 175 | null | 0 | Partition phase 1 | 760 | 1
1 | 1 | Wall tiling | Tiling | 271 | pending | 27 | null | 271 | null | 0 | Partition phase 3 | 216 | 1

## FLOOR1-GR
day_number | floor | process | assigned_trade | planned_remaining | is_valid | task_status | initial_production_rate | actual_efficiency | remain_work | is_rework | today_workload | predecessor_processes | pre_remain_work | trade_available | prerequisites_completed | can_start
0 | 1 | Gravel base layer | Gravel | 154 | FALSE | pending | 34 | null | 154 | null | null | null | null | 1 | TRUE | TRUE
1 | 1 | Gravel base layer | Gravel | 154 | FALSE | in_progress | 34 | 32 | 122 | FALSE | 32 | null | null | 0 | TRUE | FALSE
2 | 1 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 32 | 90 | FALSE | 32 | null | null | 0 | TRUE | FALSE
3 | 1 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 32 | 58 | FALSE | 32 | null | null | 0 | TRUE | FALSE
4 | 1 | Gravel base layer | Gravel | 154 | TRUE | in_progress | 34 | 33 | 25 | FALSE | 33 | null | null | 0 | TRUE | FALSE
5 | 1 | Gravel base layer | Gravel | 154 | TRUE | completed | 34 | 34 | 0 | FALSE | 25 | null | null | 1 | TRUE | FALSE

## Sheet4
35 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | pending | 41 | null | 164 | null | 0 | Partition phase 2 | 0 | 1 | TRUE | TRUE
36 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 37 | 127 | FALSE | 37 | Partition phase 2 | 0 | 0 | TRUE | FALSE
37 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 0 | 127 | TRUE | 0 | Partition phase 2 | 0 | 0 | TRUE | FALSE
38 | 1 | Electric conduits in the wall | Electricity | 164 | FALSE | in_progress | 41 | 38 | 89 | FALSE | 38 | Partition phase 2 | 0 | 0 | TRUE | FALSE
39 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | in_progress | 41 | 45 | 44 | FALSE | 45 | Partition phase 2 | 0 | 0 | TRUE | FALSE
40 | 1 | Electric conduits in the wall | Electricity | 164 | TRUE | completed | 41 | 45 | 0 | FALSE | 44 | Partition phase 2 | 0 | 1 | TRUE | FALSE

## Sheet5
day_number | floor | process | assigned_trade | IQ | task_status | initial_production_rate | actual_efficiency | remain_work | is_rework | today_workload | pre_remain_work | trade_available | can_start
30 | 3 | Floor tiling | Tiling | 661 | pending | 62 | null | 661 | null | 0 | 0, 0 | 1 | TRUE
31 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 62 | 599 | FALSE | 62 | 0, 0 | 0 | FALSE
32 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 57 | 542 | FALSE | 57 | 0, 0 | 0 | FALSE
33 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 58 | 484 | FALSE | 58 | 0, 0 | 0 | FALSE
34 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 61 | 423 | FALSE | 61 | 0, 0 | 0 | FALSE
35 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 0 | 423 | TRUE | 0 | 0, 0 | 0 | FALSE
36 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 59 | 364 | FALSE | 59 | 0, 0 | 0 | FALSE
37 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 57 | 307 | FALSE | 57 | 0, 0 | 0 | FALSE
38 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 58 | 249 | FALSE | 58 | 0, 0 | 0 | FALSE
39 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 67 | 182 | FALSE | 67 | 0, 0 | 0 | FALSE
40 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 0 | 182 | TRUE | 0 | 0, 0 | 0 | FALSE
41 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 58 | 124 | FALSE | 58 | 0, 0 | 0 | FALSE
42 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 60 | 64 | FALSE | 60 | 0, 0 | 0 | FALSE
43 | 3 | Floor tiling | Tiling | 661 | in_progress | 62 | 58 | 6 | FALSE | 58 | 0, 0 | 0 | FALSE
44 | 3 | Floor tiling | Tiling | 661 | completed | 62 | 59 | 0 | FALSE | 6 | 0, 0 | 1 | FALSE