## 50%_返工
day_number | process | floor | trade | is_invalid | is_rework | daily_work_done | efficiency | start_day | complete_day | recorded_at
1 | Gravel base layer | 1 | Gravel | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
1 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 54 | 98.18% | 0 | null | 2025-03-25 11:54:28.699895+00
2 | Gravel base layer | 1 | Gravel | FALSE | TRUE | 34 | 100% | 0 | null | 2025-03-25 11:54:28.699895+00
2 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
3 | Gravel base layer | 1 | Gravel | FALSE | TRUE | 31 | 91.18% | 0 | null | 2025-03-25 11:54:28.699895+00
3 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
4 | Gravel base layer | 1 | Gravel | FALSE | TRUE | 37 | 108.8% | 0 | null | 2025-03-25 11:54:28.699895+00
4 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
5 | Gravel base layer | 1 | Gravel | FALSE | TRUE | 36 | 105.9% | 0 | null | 2025-03-25 11:54:28.699895+00
5 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
6 | Gravel base layer | 1 | Gravel | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
6 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 53 | 96.36% | 0 | null | 2025-03-25 11:54:28.699895+00
7 | Gravel base layer | 1 | Gravel | FALSE | TRUE | 37 | 108.8% | 0 | 7 | 2025-03-25 11:54:28.699895+00
7 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 54 | 98.18% | 0 | null | 2025-03-25 11:54:28.699895+00
8 | Electric conduits in the floor | 1 | Electricity | FALSE | TRUE | 51 | 100% | 7 | null | 2025-03-25 11:54:28.699895+00
8 | Gravel base layer | 2 | Gravel | TRUE | TRUE | 0 | 0% | 7 | null | 2025-03-25 11:54:28.699895+00
8 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 60 | 109.1% | 0 | null | 2025-03-25 11:54:28.699895+00
8 | Pipes in the floor | 1 | Plumbing | FALSE | TRUE | 74 | 107.2% | 7 | null | 2025-03-25 11:54:28.699895+00
9 | Electric conduits in the floor | 1 | Electricity | TRUE | TRUE | 0 | 0% | 7 | null | 2025-03-25 11:54:28.699895+00
9 | Gravel base layer | 2 | Gravel | FALSE | TRUE | 33 | 97.06% | 7 | null | 2025-03-25 11:54:28.699895+00
9 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 53 | 96.36% | 0 | null | 2025-03-25 11:54:28.699895+00
9 | Pipes in the floor | 1 | Plumbing | TRUE | TRUE | 0 | 0% | 7 | null | 2025-03-25 11:54:28.699895+00
10 | Electric conduits in the floor | 1 | Electricity | TRUE | TRUE | 0 | 0% | 7 | null | 2025-03-25 11:54:28.699895+00
10 | Gravel base layer | 2 | Gravel | FALSE | TRUE | 36 | 105.9% | 7 | null | 2025-03-25 11:54:28.699895+00
10 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 54 | 98.18% | 0 | null | 2025-03-25 11:54:28.699895+00
10 | Pipes in the floor | 1 | Plumbing | FALSE | TRUE | 66 | 95.65% | 7 | 10 | 2025-03-25 11:54:28.699895+00
11 | Electric conduits in the floor | 1 | Electricity | FALSE | TRUE | 54 | 105.9% | 7 | 11 | 2025-03-25 11:54:28.699895+00
11 | Gravel base layer | 2 | Gravel | FALSE | TRUE | 33 | 97.06% | 7 | null | 2025-03-25 11:54:28.699895+00
11 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 55 | 100% | 0 | null | 2025-03-25 11:54:28.699895+00
12 | Floor tiling | 1 | Tiling | FALSE | TRUE | 61 | 98.39% | 11 | null | 2025-03-25 11:54:28.699895+00
12 | Gravel base layer | 2 | Gravel | FALSE | TRUE | 31 | 91.18% | 7 | null | 2025-03-25 11:54:28.699895+00
12 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 60 | 109.1% | 0 | null | 2025-03-25 11:54:28.699895+00
13 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
13 | Gravel base layer | 2 | Gravel | FALSE | TRUE | 33 | 97.06% | 7 | 13 | 2025-03-25 11:54:28.699895+00
13 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
14 | Electric conduits in the floor | 2 | Electricity | FALSE | TRUE | 56 | 109.8% | 13 | null | 2025-03-25 11:54:28.699895+00
14 | Floor tiling | 1 | Tiling | FALSE | TRUE | 56 | 90.32% | 11 | null | 2025-03-25 11:54:28.699895+00
14 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
14 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
14 | Pipes in the floor | 2 | Plumbing | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
15 | Electric conduits in the floor | 2 | Electricity | FALSE | TRUE | 49 | 96.08% | 13 | 15 | 2025-03-25 11:54:28.699895+00
15 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
15 | Gravel base layer | 3 | Gravel | FALSE | TRUE | 36 | 105.9% | 13 | null | 2025-03-25 11:54:28.699895+00
15 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
15 | Pipes in the floor | 2 | Plumbing | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
16 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
16 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
16 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
16 | Pipes in the floor | 2 | Plumbing | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
17 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
17 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
17 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
17 | Pipes in the floor | 2 | Plumbing | FALSE | TRUE | 72 | 104.4% | 13 | null | 2025-03-25 11:54:28.699895+00
18 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
18 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
18 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 53 | 96.36% | 0 | null | 2025-03-25 11:54:28.699895+00
18 | Pipes in the floor | 2 | Plumbing | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
19 | Floor tiling | 1 | Tiling | FALSE | TRUE | 66 | 106.5% | 11 | null | 2025-03-25 11:54:28.699895+00
19 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
19 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
19 | Pipes in the floor | 2 | Plumbing | FALSE | TRUE | 68 | 98.55% | 13 | 19 | 2025-03-25 11:54:28.699895+00
20 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
20 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
20 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
21 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
21 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
21 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
22 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
22 | Gravel base layer | 3 | Gravel | FALSE | TRUE | 37 | 108.8% | 13 | null | 2025-03-25 11:54:28.699895+00
22 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
23 | Floor tiling | 1 | Tiling | FALSE | TRUE | 66 | 106.5% | 11 | null | 2025-03-25 11:54:28.699895+00
23 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
23 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 51 | 92.73% | 0 | null | 2025-03-25 11:54:28.699895+00
24 | Floor tiling | 1 | Tiling | FALSE | TRUE | 57 | 91.94% | 11 | null | 2025-03-25 11:54:28.699895+00
24 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
24 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 55 | 100% | 0 | null | 2025-03-25 11:54:28.699895+00
25 | Floor tiling | 1 | Tiling | FALSE | TRUE | 65 | 104.8% | 11 | null | 2025-03-25 11:54:28.699895+00
25 | Gravel base layer | 3 | Gravel | FALSE | TRUE | 37 | 108.8% | 13 | null | 2025-03-25 11:54:28.699895+00
25 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 53 | 96.36% | 0 | null | 2025-03-25 11:54:28.699895+00
26 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
26 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
26 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
27 | Floor tiling | 1 | Tiling | FALSE | TRUE | 64 | 103.2% | 11 | null | 2025-03-25 11:54:28.699895+00
27 | Gravel base layer | 3 | Gravel | FALSE | TRUE | 35 | 102.9% | 13 | null | 2025-03-25 11:54:28.699895+00
27 | Partition phase 1 | 1 | Partition | TRUE | TRUE | 0 | 0% | 0 | null | 2025-03-25 11:54:28.699895+00
28 | Floor tiling | 1 | Tiling | FALSE | TRUE | 56 | 90.32% | 11 | null | 2025-03-25 11:54:28.699895+00
28 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
28 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 59 | 107.3% | 0 | null | 2025-03-25 11:54:28.699895+00
29 | Floor tiling | 1 | Tiling | FALSE | TRUE | 62 | 100% | 11 | null | 2025-03-25 11:54:28.699895+00
29 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
29 | Partition phase 1 | 1 | Partition | FALSE | TRUE | 59 | 107.3% | 0 | 29 | 2025-03-25 11:54:28.699895+00
30 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
30 | Gravel base layer | 3 | Gravel | TRUE | TRUE | 0 | 0% | 13 | null | 2025-03-25 11:54:28.699895+00
30 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
30 | Pipes in the wall | 1 | Plumbing | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
31 | Floor tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 11 | null | 2025-03-25 11:54:28.699895+00
31 | Gravel base layer | 3 | Gravel | FALSE | TRUE | 35 | 102.9% | 13 | 31 | 2025-03-25 11:54:28.699895+00
31 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 60 | 109.1% | 29 | null | 2025-03-25 11:54:28.699895+00
31 | Pipes in the wall | 1 | Plumbing | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
32 | Electric conduits in the floor | 3 | Electricity | FALSE | TRUE | 51 | 100% | 31 | null | 2025-03-25 11:54:28.699895+00
32 | Floor tiling | 1 | Tiling | FALSE | TRUE | 64 | 103.2% | 11 | null | 2025-03-25 11:54:28.699895+00
32 | Gravel base layer | 4 | Gravel | TRUE | TRUE | 0 | 0% | 31 | null | 2025-03-25 11:54:28.699895+00
32 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 52 | 94.55% | 29 | null | 2025-03-25 11:54:28.699895+00
32 | Pipes in the wall | 1 | Plumbing | FALSE | TRUE | 35 | 94.59% | 29 | null | 2025-03-25 11:54:28.699895+00
33 | Electric conduits in the floor | 3 | Electricity | FALSE | TRUE | 53 | 103.9% | 31 | 33 | 2025-03-25 11:54:28.699895+00
33 | Floor tiling | 1 | Tiling | FALSE | TRUE | 66 | 106.5% | 11 | null | 2025-03-25 11:54:28.699895+00
33 | Gravel base layer | 4 | Gravel | TRUE | TRUE | 0 | 0% | 31 | null | 2025-03-25 11:54:28.699895+00
33 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 52 | 94.55% | 29 | null | 2025-03-25 11:54:28.699895+00
33 | Pipes in the wall | 1 | Plumbing | FALSE | TRUE | 33 | 89.19% | 29 | null | 2025-03-25 11:54:28.699895+00
34 | Floor tiling | 1 | Tiling | FALSE | TRUE | 59 | 95.16% | 11 | null | 2025-03-25 11:54:28.699895+00
34 | Gravel base layer | 4 | Gravel | TRUE | TRUE | 0 | 0% | 31 | null | 2025-03-25 11:54:28.699895+00
34 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 58 | 105.5% | 29 | null | 2025-03-25 11:54:28.699895+00
34 | Pipes in the wall | 1 | Plumbing | FALSE | TRUE | 33 | 89.19% | 29 | null | 2025-03-25 11:54:28.699895+00
35 | Floor tiling | 1 | Tiling | FALSE | TRUE | 56 | 90.32% | 11 | 35 | 2025-03-25 11:54:28.699895+00
35 | Gravel base layer | 4 | Gravel | TRUE | TRUE | 0 | 0% | 31 | null | 2025-03-25 11:54:28.699895+00
35 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
35 | Pipes in the wall | 1 | Plumbing | FALSE | TRUE | 37 | 100% | 29 | null | 2025-03-25 11:54:28.699895+00
36 | Floor tiling | 2 | Tiling | FALSE | TRUE | 63 | 101.6% | 35 | null | 2025-03-25 11:54:28.699895+00
36 | Gravel base layer | 4 | Gravel | TRUE | TRUE | 0 | 0% | 31 | null | 2025-03-25 11:54:28.699895+00
36 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 58 | 105.5% | 29 | null | 2025-03-25 11:54:28.699895+00
36 | Pipes in the wall | 1 | Plumbing | FALSE | TRUE | 37 | 100% | 29 | null | 2025-03-25 11:54:28.699895+00
37 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
37 | Gravel base layer | 4 | Gravel | FALSE | TRUE | 35 | 102.9% | 31 | null | 2025-03-25 11:54:28.699895+00
37 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
37 | Pipes in the wall | 1 | Plumbing | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
38 | Floor tiling | 2 | Tiling | FALSE | TRUE | 63 | 101.6% | 35 | null | 2025-03-25 11:54:28.699895+00
38 | Gravel base layer | 4 | Gravel | TRUE | TRUE | 0 | 0% | 31 | null | 2025-03-25 11:54:28.699895+00
38 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
38 | Pipes in the wall | 1 | Plumbing | FALSE | TRUE | 35 | 94.59% | 29 | 38 | 2025-03-25 11:54:28.699895+00
39 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
39 | Gravel base layer | 4 | Gravel | FALSE | TRUE | 31 | 91.18% | 31 | null | 2025-03-25 11:54:28.699895+00
39 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
39 | Pipes in the floor | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 38 | null | 2025-03-25 11:54:28.699895+00
40 | Floor tiling | 2 | Tiling | FALSE | TRUE | 58 | 93.55% | 35 | null | 2025-03-25 11:54:28.699895+00
40 | Gravel base layer | 4 | Gravel | FALSE | TRUE | 31 | 91.18% | 31 | null | 2025-03-25 11:54:28.699895+00
40 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
40 | Pipes in the floor | 3 | Plumbing | FALSE | TRUE | 72 | 104.4% | 38 | null | 2025-03-25 11:54:28.699895+00
41 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
41 | Gravel base layer | 4 | Gravel | FALSE | TRUE | 34 | 100% | 31 | null | 2025-03-25 11:54:28.699895+00
41 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
41 | Pipes in the floor | 3 | Plumbing | FALSE | TRUE | 74 | 107.2% | 38 | 41 | 2025-03-25 11:54:28.699895+00
42 | Floor tiling | 2 | Tiling | FALSE | TRUE | 56 | 90.32% | 35 | null | 2025-03-25 11:54:28.699895+00
42 | Gravel base layer | 4 | Gravel | TRUE | TRUE | 0 | 0% | 31 | null | 2025-03-25 11:54:28.699895+00
42 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
43 | Floor tiling | 2 | Tiling | FALSE | TRUE | 64 | 103.2% | 35 | null | 2025-03-25 11:54:28.699895+00
43 | Gravel base layer | 4 | Gravel | TRUE | TRUE | 0 | 0% | 31 | null | 2025-03-25 11:54:28.699895+00
43 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
44 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
44 | Gravel base layer | 4 | Gravel | FALSE | TRUE | 33 | 97.06% | 31 | 44 | 2025-03-25 11:54:28.699895+00
44 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 50 | 90.91% | 29 | null | 2025-03-25 11:54:28.699895+00
45 | Electric conduits in the floor | 4 | Electricity | FALSE | TRUE | 54 | 105.9% | 44 | null | 2025-03-25 11:54:28.699895+00
45 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
45 | Gravel base layer | 5 | Gravel | FALSE | TRUE | 37 | 108.8% | 44 | null | 2025-03-25 11:54:28.699895+00
45 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 53 | 96.36% | 29 | null | 2025-03-25 11:54:28.699895+00
45 | Pipes in the floor | 4 | Plumbing | FALSE | TRUE | 72 | 104.4% | 44 | null | 2025-03-25 11:54:28.699895+00
46 | Electric conduits in the floor | 4 | Electricity | FALSE | TRUE | 54 | 105.9% | 44 | 46 | 2025-03-25 11:54:28.699895+00
46 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
46 | Gravel base layer | 5 | Gravel | TRUE | TRUE | 0 | 0% | 44 | null | 2025-03-25 11:54:28.699895+00
46 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 60 | 109.1% | 29 | null | 2025-03-25 11:54:28.699895+00
46 | Pipes in the floor | 4 | Plumbing | TRUE | TRUE | 0 | 0% | 44 | null | 2025-03-25 11:54:28.699895+00
47 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
47 | Gravel base layer | 5 | Gravel | TRUE | TRUE | 0 | 0% | 44 | null | 2025-03-25 11:54:28.699895+00
47 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
47 | Pipes in the floor | 4 | Plumbing | TRUE | TRUE | 0 | 0% | 44 | null | 2025-03-25 11:54:28.699895+00
48 | Floor tiling | 2 | Tiling | FALSE | TRUE | 63 | 101.6% | 35 | null | 2025-03-25 11:54:28.699895+00
48 | Gravel base layer | 5 | Gravel | FALSE | TRUE | 33 | 97.06% | 44 | null | 2025-03-25 11:54:28.699895+00
48 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 55 | 100% | 29 | null | 2025-03-25 11:54:28.699895+00
48 | Pipes in the floor | 4 | Plumbing | FALSE | TRUE | 72 | 104.4% | 44 | 48 | 2025-03-25 11:54:28.699895+00
49 | Floor tiling | 2 | Tiling | FALSE | TRUE | 64 | 103.2% | 35 | null | 2025-03-25 11:54:28.699895+00
49 | Gravel base layer | 5 | Gravel | TRUE | TRUE | 0 | 0% | 44 | null | 2025-03-25 11:54:28.699895+00
49 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 54 | 98.18% | 29 | null | 2025-03-25 11:54:28.699895+00
50 | Floor tiling | 2 | Tiling | FALSE | TRUE | 63 | 101.6% | 35 | null | 2025-03-25 11:54:28.699895+00
50 | Gravel base layer | 5 | Gravel | FALSE | TRUE | 33 | 97.06% | 44 | null | 2025-03-25 11:54:28.699895+00
50 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 54 | 98.18% | 29 | null | 2025-03-25 11:54:28.699895+00
51 | Floor tiling | 2 | Tiling | FALSE | TRUE | 64 | 103.2% | 35 | null | 2025-03-25 11:54:28.699895+00
51 | Gravel base layer | 5 | Gravel | FALSE | TRUE | 32 | 94.12% | 44 | null | 2025-03-25 11:54:28.699895+00
51 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 59 | 107.3% | 29 | null | 2025-03-25 11:54:28.699895+00
52 | Floor tiling | 2 | Tiling | FALSE | TRUE | 62 | 100% | 35 | null | 2025-03-25 11:54:28.699895+00
52 | Gravel base layer | 5 | Gravel | TRUE | TRUE | 0 | 0% | 44 | null | 2025-03-25 11:54:28.699895+00
52 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 60 | 109.1% | 29 | null | 2025-03-25 11:54:28.699895+00
53 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
53 | Gravel base layer | 5 | Gravel | TRUE | TRUE | 0 | 0% | 44 | null | 2025-03-25 11:54:28.699895+00
53 | Partition phase 1 | 2 | Partition | TRUE | TRUE | 0 | 0% | 29 | null | 2025-03-25 11:54:28.699895+00
54 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
54 | Gravel base layer | 5 | Gravel | FALSE | TRUE | 34 | 100% | 44 | 54 | 2025-03-25 11:54:28.699895+00
54 | Partition phase 1 | 2 | Partition | FALSE | TRUE | 60 | 109.1% | 29 | 54 | 2025-03-25 11:54:28.699895+00
55 | Electric conduits in the floor | 5 | Electricity | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
55 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
55 | Partition phase 2 | 1 | Partition | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
55 | Pipes in the wall | 2 | Plumbing | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
56 | Electric conduits in the floor | 5 | Electricity | FALSE | TRUE | 54 | 105.9% | 54 | null | 2025-03-25 11:54:28.699895+00
56 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
56 | Partition phase 2 | 1 | Partition | FALSE | TRUE | 48 | 94.12% | 54 | 56 | 2025-03-25 11:54:28.699895+00
56 | Pipes in the wall | 2 | Plumbing | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
57 | Electric conduits in the floor | 5 | Electricity | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
57 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
57 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 56 | 101.8% | 56 | null | 2025-03-25 11:54:28.699895+00
57 | Pipes in the wall | 2 | Plumbing | FALSE | TRUE | 35 | 94.59% | 54 | null | 2025-03-25 11:54:28.699895+00
58 | Electric conduits in the floor | 5 | Electricity | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
58 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
58 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 60 | 109.1% | 56 | null | 2025-03-25 11:54:28.699895+00
58 | Pipes in the wall | 2 | Plumbing | FALSE | TRUE | 39 | 105.4% | 54 | null | 2025-03-25 11:54:28.699895+00
59 | Electric conduits in the floor | 5 | Electricity | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
59 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
59 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
59 | Pipes in the wall | 2 | Plumbing | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
60 | Electric conduits in the floor | 5 | Electricity | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
60 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
60 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 53 | 96.36% | 56 | null | 2025-03-25 11:54:28.699895+00
60 | Pipes in the wall | 2 | Plumbing | FALSE | TRUE | 39 | 105.4% | 54 | null | 2025-03-25 11:54:28.699895+00
61 | Electric conduits in the floor | 5 | Electricity | FALSE | TRUE | 54 | 105.9% | 54 | 61 | 2025-03-25 11:54:28.699895+00
61 | Floor tiling | 2 | Tiling | FALSE | TRUE | 64 | 103.2% | 35 | null | 2025-03-25 11:54:28.699895+00
61 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 60 | 109.1% | 56 | null | 2025-03-25 11:54:28.699895+00
61 | Pipes in the wall | 2 | Plumbing | FALSE | TRUE | 33 | 89.19% | 54 | null | 2025-03-25 11:54:28.699895+00
62 | Electric conduits in the wall | 1 | Electricity | FALSE | TRUE | 40 | 97.56% | 61 | null | 2025-03-25 11:54:28.699895+00
62 | Floor tiling | 2 | Tiling | FALSE | TRUE | 65 | 104.8% | 35 | null | 2025-03-25 11:54:28.699895+00
62 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
62 | Pipes in the wall | 2 | Plumbing | FALSE | TRUE | 35 | 94.59% | 54 | null | 2025-03-25 11:54:28.699895+00
63 | Electric conduits in the wall | 1 | Electricity | TRUE | TRUE | 0 | 0% | 61 | null | 2025-03-25 11:54:28.699895+00
63 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
63 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
63 | Pipes in the wall | 2 | Plumbing | TRUE | TRUE | 0 | 0% | 54 | null | 2025-03-25 11:54:28.699895+00
64 | Electric conduits in the wall | 1 | Electricity | FALSE | TRUE | 38 | 92.68% | 61 | null | 2025-03-25 11:54:28.699895+00
64 | Floor tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 35 | null | 2025-03-25 11:54:28.699895+00
64 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 53 | 96.36% | 56 | null | 2025-03-25 11:54:28.699895+00
64 | Pipes in the wall | 2 | Plumbing | FALSE | TRUE | 35 | 94.59% | 54 | 64 | 2025-03-25 11:54:28.699895+00
65 | Electric conduits in the wall | 1 | Electricity | FALSE | TRUE | 40 | 97.56% | 61 | null | 2025-03-25 11:54:28.699895+00
65 | Floor tiling | 2 | Tiling | FALSE | TRUE | 57 | 91.94% | 35 | 65 | 2025-03-25 11:54:28.699895+00
65 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 53 | 96.36% | 56 | null | 2025-03-25 11:54:28.699895+00
65 | Pipes in the floor | 5 | Plumbing | FALSE | TRUE | 70 | 101.4% | 64 | null | 2025-03-25 11:54:28.699895+00
66 | Electric conduits in the wall | 1 | Electricity | FALSE | TRUE | 37 | 90.24% | 61 | null | 2025-03-25 11:54:28.699895+00
66 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
66 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 58 | 105.5% | 56 | null | 2025-03-25 11:54:28.699895+00
66 | Pipes in the floor | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 64 | null | 2025-03-25 11:54:28.699895+00
67 | Electric conduits in the wall | 1 | Electricity | FALSE | TRUE | 38 | 92.68% | 61 | 67 | 2025-03-25 11:54:28.699895+00
67 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
67 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
67 | Pipes in the floor | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 64 | null | 2025-03-25 11:54:28.699895+00
68 | Floor tiling | 3 | Tiling | FALSE | TRUE | 64 | 103.2% | 65 | null | 2025-03-25 11:54:28.699895+00
68 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
68 | Pipes in the floor | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 64 | null | 2025-03-25 11:54:28.699895+00
69 | Floor tiling | 3 | Tiling | FALSE | TRUE | 68 | 109.7% | 65 | null | 2025-03-25 11:54:28.699895+00
69 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 60 | 109.1% | 56 | null | 2025-03-25 11:54:28.699895+00
69 | Pipes in the floor | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 64 | null | 2025-03-25 11:54:28.699895+00
70 | Floor tiling | 3 | Tiling | FALSE | TRUE | 57 | 91.94% | 65 | null | 2025-03-25 11:54:28.699895+00
70 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 50 | 90.91% | 56 | null | 2025-03-25 11:54:28.699895+00
70 | Pipes in the floor | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 64 | null | 2025-03-25 11:54:28.699895+00
71 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
71 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
71 | Pipes in the floor | 5 | Plumbing | FALSE | TRUE | 64 | 92.75% | 64 | 71 | 2025-03-25 11:54:28.699895+00
72 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
72 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 52 | 94.55% | 56 | null | 2025-03-25 11:54:28.699895+00
73 | Floor tiling | 3 | Tiling | FALSE | TRUE | 66 | 106.5% | 65 | null | 2025-03-25 11:54:28.699895+00
73 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
74 | Floor tiling | 3 | Tiling | FALSE | TRUE | 67 | 108.1% | 65 | null | 2025-03-25 11:54:28.699895+00
74 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 54 | 98.18% | 56 | null | 2025-03-25 11:54:28.699895+00
75 | Floor tiling | 3 | Tiling | FALSE | TRUE | 68 | 109.7% | 65 | null | 2025-03-25 11:54:28.699895+00
75 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 60 | 109.1% | 56 | null | 2025-03-25 11:54:28.699895+00
76 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
76 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
77 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
77 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
78 | Floor tiling | 3 | Tiling | FALSE | TRUE | 57 | 91.94% | 65 | null | 2025-03-25 11:54:28.699895+00
78 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 58 | 105.5% | 56 | null | 2025-03-25 11:54:28.699895+00
79 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
79 | Partition phase 1 | 3 | Partition | TRUE | TRUE | 0 | 0% | 56 | null | 2025-03-25 11:54:28.699895+00
80 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
80 | Partition phase 1 | 3 | Partition | FALSE | TRUE | 53 | 96.36% | 56 | 80 | 2025-03-25 11:54:28.699895+00
81 | Floor tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 65 | null | 2025-03-25 11:54:28.699895+00
81 | Partition phase 3 | 1 | Partition | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
81 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
82 | Floor tiling | 3 | Tiling | FALSE | TRUE | 61 | 98.39% | 65 | null | 2025-03-25 11:54:28.699895+00
82 | Partition phase 3 | 1 | Partition | FALSE | TRUE | 32 | 100% | 80 | null | 2025-03-25 11:54:28.699895+00
82 | Pipes in the wall | 3 | Plumbing | FALSE | TRUE | 41 | 110.8% | 80 | null | 2025-03-25 11:54:28.699895+00
83 | Floor tiling | 3 | Tiling | FALSE | TRUE | 58 | 93.55% | 65 | null | 2025-03-25 11:54:28.699895+00
83 | Partition phase 3 | 1 | Partition | FALSE | TRUE | 34 | 106.2% | 80 | null | 2025-03-25 11:54:28.699895+00
83 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
84 | Floor tiling | 3 | Tiling | FALSE | TRUE | 58 | 93.55% | 65 | null | 2025-03-25 11:54:28.699895+00
84 | Partition phase 3 | 1 | Partition | FALSE | TRUE | 29 | 90.63% | 80 | null | 2025-03-25 11:54:28.699895+00
84 | Pipes in the wall | 3 | Plumbing | FALSE | TRUE | 36 | 97.3% | 80 | null | 2025-03-25 11:54:28.699895+00
85 | Floor tiling | 3 | Tiling | FALSE | TRUE | 59 | 95.16% | 65 | null | 2025-03-25 11:54:28.699895+00
85 | Partition phase 3 | 1 | Partition | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
85 | Pipes in the wall | 3 | Plumbing | FALSE | TRUE | 34 | 91.89% | 80 | null | 2025-03-25 11:54:28.699895+00
86 | Floor tiling | 3 | Tiling | FALSE | TRUE | 66 | 106.5% | 65 | null | 2025-03-25 11:54:28.699895+00
86 | Partition phase 3 | 1 | Partition | FALSE | TRUE | 30 | 93.75% | 80 | null | 2025-03-25 11:54:28.699895+00
86 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
87 | Floor tiling | 3 | Tiling | FALSE | TRUE | 64 | 103.2% | 65 | 87 | 2025-03-25 11:54:28.699895+00
87 | Partition phase 3 | 1 | Partition | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
87 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
88 | Floor tiling | 4 | Tiling | FALSE | TRUE | 60 | 96.77% | 87 | null | 2025-03-25 11:54:28.699895+00
88 | Partition phase 3 | 1 | Partition | FALSE | TRUE | 32 | 100% | 80 | null | 2025-03-25 11:54:28.699895+00
88 | Pipes in the wall | 3 | Plumbing | FALSE | TRUE | 35 | 94.59% | 80 | null | 2025-03-25 11:54:28.699895+00
89 | Floor tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 87 | null | 2025-03-25 11:54:28.699895+00
89 | Partition phase 3 | 1 | Partition | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
89 | Pipes in the wall | 3 | Plumbing | FALSE | TRUE | 35 | 94.59% | 80 | null | 2025-03-25 11:54:28.699895+00
90 | Floor tiling | 4 | Tiling | FALSE | TRUE | 56 | 90.32% | 87 | null | 2025-03-25 11:54:28.699895+00
90 | Partition phase 3 | 1 | Partition | FALSE | TRUE | 35 | 109.4% | 80 | null | 2025-03-25 11:54:28.699895+00
90 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
91 | Floor tiling | 4 | Tiling | FALSE | TRUE | 56 | 90.32% | 87 | null | 2025-03-25 11:54:28.699895+00
91 | Partition phase 3 | 1 | Partition | FALSE | TRUE | 31 | 96.88% | 80 | 91 | 2025-03-25 11:54:28.699895+00
91 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
92 | Floor tiling | 4 | Tiling | FALSE | TRUE | 62 | 100% | 87 | null | 2025-03-25 11:54:28.699895+00
92 | Partition phase 2 | 2 | Partition | FALSE | TRUE | 53 | 103.9% | 91 | 92 | 2025-03-25 11:54:28.699895+00
92 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
93 | Electric conduits in the wall | 2 | Electricity | FALSE | TRUE | 40 | 97.56% | 92 | null | 2025-03-25 11:54:28.699895+00
93 | Floor tiling | 4 | Tiling | FALSE | TRUE | 56 | 90.32% | 87 | null | 2025-03-25 11:54:28.699895+00
93 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 51 | 92.73% | 92 | null | 2025-03-25 11:54:28.699895+00
93 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
94 | Electric conduits in the wall | 2 | Electricity | FALSE | TRUE | 42 | 102.4% | 92 | null | 2025-03-25 11:54:28.699895+00
94 | Floor tiling | 4 | Tiling | FALSE | TRUE | 60 | 96.77% | 87 | null | 2025-03-25 11:54:28.699895+00
94 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
94 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
95 | Electric conduits in the wall | 2 | Electricity | FALSE | TRUE | 40 | 97.56% | 92 | null | 2025-03-25 11:54:28.699895+00
95 | Floor tiling | 4 | Tiling | FALSE | TRUE | 67 | 108.1% | 87 | null | 2025-03-25 11:54:28.699895+00
95 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
95 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
96 | Electric conduits in the wall | 2 | Electricity | FALSE | TRUE | 43 | 104.9% | 92 | null | 2025-03-25 11:54:28.699895+00
96 | Floor tiling | 4 | Tiling | FALSE | TRUE | 61 | 98.39% | 87 | null | 2025-03-25 11:54:28.699895+00
96 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
96 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
97 | Electric conduits in the wall | 2 | Electricity | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
97 | Floor tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 87 | null | 2025-03-25 11:54:28.699895+00
97 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
97 | Pipes in the wall | 3 | Plumbing | TRUE | TRUE | 0 | 0% | 80 | null | 2025-03-25 11:54:28.699895+00
98 | Electric conduits in the wall | 2 | Electricity | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
98 | Floor tiling | 4 | Tiling | FALSE | TRUE | 68 | 109.7% | 87 | null | 2025-03-25 11:54:28.699895+00
98 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 54 | 98.18% | 92 | null | 2025-03-25 11:54:28.699895+00
98 | Pipes in the wall | 3 | Plumbing | FALSE | TRUE | 40 | 108.1% | 80 | 98 | 2025-03-25 11:54:28.699895+00
99 | Electric conduits in the wall | 2 | Electricity | FALSE | TRUE | 39 | 95.12% | 92 | 99 | 2025-03-25 11:54:28.699895+00
99 | Floor tiling | 4 | Tiling | FALSE | TRUE | 64 | 103.2% | 87 | null | 2025-03-25 11:54:28.699895+00
99 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 54 | 98.18% | 92 | null | 2025-03-25 11:54:28.699895+00
100 | Floor tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 87 | null | 2025-03-25 11:54:28.699895+00
100 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
101 | Floor tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 87 | null | 2025-03-25 11:54:28.699895+00
101 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
102 | Floor tiling | 4 | Tiling | FALSE | TRUE | 59 | 95.16% | 87 | null | 2025-03-25 11:54:28.699895+00
102 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 59 | 107.3% | 92 | null | 2025-03-25 11:54:28.699895+00
103 | Floor tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 87 | null | 2025-03-25 11:54:28.699895+00
103 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 53 | 96.36% | 92 | null | 2025-03-25 11:54:28.699895+00
104 | Floor tiling | 4 | Tiling | FALSE | TRUE | 63 | 101.6% | 87 | null | 2025-03-25 11:54:28.699895+00
104 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
105 | Floor tiling | 4 | Tiling | FALSE | TRUE | 68 | 109.7% | 87 | 105 | 2025-03-25 11:54:28.699895+00
105 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 56 | 101.8% | 92 | null | 2025-03-25 11:54:28.699895+00
106 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 56 | 101.8% | 92 | null | 2025-03-25 11:54:28.699895+00
106 | Wall tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 105 | null | 2025-03-25 11:54:28.699895+00
107 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 60 | 109.1% | 92 | null | 2025-03-25 11:54:28.699895+00
107 | Wall tiling | 1 | Tiling | FALSE | TRUE | 26 | 96.3% | 105 | null | 2025-03-25 11:54:28.699895+00
108 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
108 | Wall tiling | 1 | Tiling | FALSE | TRUE | 25 | 92.59% | 105 | null | 2025-03-25 11:54:28.699895+00
109 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 52 | 94.55% | 92 | null | 2025-03-25 11:54:28.699895+00
109 | Wall tiling | 1 | Tiling | FALSE | TRUE | 26 | 96.3% | 105 | null | 2025-03-25 11:54:28.699895+00
110 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
110 | Wall tiling | 1 | Tiling | FALSE | TRUE | 29 | 107.4% | 105 | null | 2025-03-25 11:54:28.699895+00
111 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 50 | 90.91% | 92 | null | 2025-03-25 11:54:28.699895+00
111 | Wall tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 105 | null | 2025-03-25 11:54:28.699895+00
112 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 50 | 90.91% | 92 | null | 2025-03-25 11:54:28.699895+00
112 | Wall tiling | 1 | Tiling | FALSE | TRUE | 24 | 88.89% | 105 | null | 2025-03-25 11:54:28.699895+00
113 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
113 | Wall tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 105 | null | 2025-03-25 11:54:28.699895+00
114 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 59 | 107.3% | 92 | null | 2025-03-25 11:54:28.699895+00
114 | Wall tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 105 | null | 2025-03-25 11:54:28.699895+00
115 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
115 | Wall tiling | 1 | Tiling | FALSE | TRUE | 29 | 107.4% | 105 | null | 2025-03-25 11:54:28.699895+00
116 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
116 | Wall tiling | 1 | Tiling | FALSE | TRUE | 29 | 107.4% | 105 | null | 2025-03-25 11:54:28.699895+00
117 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
117 | Wall tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 105 | null | 2025-03-25 11:54:28.699895+00
118 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 52 | 94.55% | 92 | null | 2025-03-25 11:54:28.699895+00
118 | Wall tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 105 | null | 2025-03-25 11:54:28.699895+00
119 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 55 | 100% | 92 | null | 2025-03-25 11:54:28.699895+00
119 | Wall tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 105 | null | 2025-03-25 11:54:28.699895+00
120 | Partition phase 1 | 4 | Partition | TRUE | TRUE | 0 | 0% | 92 | null | 2025-03-25 11:54:28.699895+00
120 | Wall tiling | 1 | Tiling | FALSE | TRUE | 30 | 111.1% | 105 | null | 2025-03-25 11:54:28.699895+00
121 | Partition phase 1 | 4 | Partition | FALSE | TRUE | 51 | 92.73% | 92 | 121 | 2025-03-25 11:54:28.699895+00
121 | Wall tiling | 1 | Tiling | TRUE | TRUE | 0 | 0% | 105 | null | 2025-03-25 11:54:28.699895+00
122 | Partition phase 3 | 2 | Partition | FALSE | TRUE | 33 | 103.1% | 121 | null | 2025-03-25 11:54:28.699895+00
122 | Pipes in the wall | 4 | Plumbing | FALSE | TRUE | 40 | 108.1% | 121 | null | 2025-03-25 11:54:28.699895+00
122 | Wall tiling | 1 | Tiling | FALSE | TRUE | 25 | 92.59% | 105 | null | 2025-03-25 11:54:28.699895+00
123 | Partition phase 3 | 2 | Partition | TRUE | TRUE | 0 | 0% | 121 | null | 2025-03-25 11:54:28.699895+00
123 | Pipes in the wall | 4 | Plumbing | FALSE | TRUE | 37 | 100% | 121 | null | 2025-03-25 11:54:28.699895+00
123 | Wall tiling | 1 | Tiling | FALSE | TRUE | 29 | 107.4% | 105 | null | 2025-03-25 11:54:28.699895+00
124 | Partition phase 3 | 2 | Partition | FALSE | TRUE | 29 | 90.63% | 121 | null | 2025-03-25 11:54:28.699895+00
124 | Pipes in the wall | 4 | Plumbing | FALSE | TRUE | 37 | 100% | 121 | null | 2025-03-25 11:54:28.699895+00
124 | Wall tiling | 1 | Tiling | FALSE | TRUE | 26 | 96.3% | 105 | 124 | 2025-03-25 11:54:28.699895+00
125 | Floor tiling | 5 | Tiling | FALSE | TRUE | 62 | 100% | 124 | null | 2025-03-25 11:54:28.699895+00
125 | Partition phase 3 | 2 | Partition | FALSE | TRUE | 29 | 90.63% | 121 | null | 2025-03-25 11:54:28.699895+00
125 | Pipes in the wall | 4 | Plumbing | FALSE | TRUE | 37 | 100% | 121 | null | 2025-03-25 11:54:28.699895+00
126 | Floor tiling | 5 | Tiling | FALSE | TRUE | 61 | 98.39% | 124 | null | 2025-03-25 11:54:28.699895+00
126 | Partition phase 3 | 2 | Partition | TRUE | TRUE | 0 | 0% | 121 | null | 2025-03-25 11:54:28.699895+00
126 | Pipes in the wall | 4 | Plumbing | FALSE | TRUE | 34 | 91.89% | 121 | null | 2025-03-25 11:54:28.699895+00
127 | Floor tiling | 5 | Tiling | FALSE | TRUE | 58 | 93.55% | 124 | null | 2025-03-25 11:54:28.699895+00
127 | Partition phase 3 | 2 | Partition | TRUE | TRUE | 0 | 0% | 121 | null | 2025-03-25 11:54:28.699895+00
127 | Pipes in the wall | 4 | Plumbing | TRUE | TRUE | 0 | 0% | 121 | null | 2025-03-25 11:54:28.699895+00
128 | Floor tiling | 5 | Tiling | FALSE | TRUE | 67 | 108.1% | 124 | null | 2025-03-25 11:54:28.699895+00
128 | Partition phase 3 | 2 | Partition | FALSE | TRUE | 30 | 93.75% | 121 | null | 2025-03-25 11:54:28.699895+00
128 | Pipes in the wall | 4 | Plumbing | TRUE | TRUE | 0 | 0% | 121 | null | 2025-03-25 11:54:28.699895+00
129 | Floor tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 124 | null | 2025-03-25 11:54:28.699895+00
129 | Partition phase 3 | 2 | Partition | FALSE | TRUE | 30 | 93.75% | 121 | null | 2025-03-25 11:54:28.699895+00
129 | Pipes in the wall | 4 | Plumbing | TRUE | TRUE | 0 | 0% | 121 | null | 2025-03-25 11:54:28.699895+00
130 | Floor tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 124 | null | 2025-03-25 11:54:28.699895+00
130 | Partition phase 3 | 2 | Partition | FALSE | TRUE | 31 | 96.88% | 121 | null | 2025-03-25 11:54:28.699895+00
130 | Pipes in the wall | 4 | Plumbing | FALSE | TRUE | 38 | 102.7% | 121 | 130 | 2025-03-25 11:54:28.699895+00
131 | Floor tiling | 5 | Tiling | FALSE | TRUE | 68 | 109.7% | 124 | null | 2025-03-25 11:54:28.699895+00
131 | Partition phase 3 | 2 | Partition | FALSE | TRUE | 32 | 100% | 121 | null | 2025-03-25 11:54:28.699895+00
132 | Floor tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 124 | null | 2025-03-25 11:54:28.699895+00
132 | Partition phase 3 | 2 | Partition | FALSE | TRUE | 31 | 96.88% | 121 | 132 | 2025-03-25 11:54:28.699895+00
133 | Floor tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 124 | null | 2025-03-25 11:54:28.699895+00
133 | Partition phase 2 | 3 | Partition | FALSE | TRUE | 48 | 94.12% | 132 | 133 | 2025-03-25 11:54:28.699895+00
134 | Electric conduits in the wall | 3 | Electricity | FALSE | TRUE | 38 | 92.68% | 133 | null | 2025-03-25 11:54:28.699895+00
134 | Floor tiling | 5 | Tiling | FALSE | TRUE | 62 | 100% | 124 | null | 2025-03-25 11:54:28.699895+00
134 | Partition phase 2 | 4 | Partition | FALSE | TRUE | 51 | 100% | 133 | 134 | 2025-03-25 11:54:28.699895+00
135 | Electric conduits in the wall | 3 | Electricity | FALSE | TRUE | 44 | 107.3% | 133 | null | 2025-03-25 11:54:28.699895+00
135 | Floor tiling | 5 | Tiling | FALSE | TRUE | 61 | 98.39% | 124 | null | 2025-03-25 11:54:28.699895+00
135 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 60 | 109.1% | 134 | null | 2025-03-25 11:54:28.699895+00
136 | Electric conduits in the wall | 3 | Electricity | TRUE | TRUE | 0 | 0% | 133 | null | 2025-03-25 11:54:28.699895+00
136 | Floor tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 124 | null | 2025-03-25 11:54:28.699895+00
136 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
137 | Electric conduits in the wall | 3 | Electricity | TRUE | TRUE | 0 | 0% | 133 | null | 2025-03-25 11:54:28.699895+00
137 | Floor tiling | 5 | Tiling | FALSE | TRUE | 61 | 98.39% | 124 | null | 2025-03-25 11:54:28.699895+00
137 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 55 | 100% | 134 | null | 2025-03-25 11:54:28.699895+00
138 | Electric conduits in the wall | 3 | Electricity | TRUE | TRUE | 0 | 0% | 133 | null | 2025-03-25 11:54:28.699895+00
138 | Floor tiling | 5 | Tiling | FALSE | TRUE | 67 | 108.1% | 124 | null | 2025-03-25 11:54:28.699895+00
138 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 55 | 100% | 134 | null | 2025-03-25 11:54:28.699895+00
139 | Electric conduits in the wall | 3 | Electricity | FALSE | TRUE | 38 | 92.68% | 133 | null | 2025-03-25 11:54:28.699895+00
139 | Floor tiling | 5 | Tiling | FALSE | TRUE | 68 | 109.7% | 124 | null | 2025-03-25 11:54:28.699895+00
139 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
140 | Electric conduits in the wall | 3 | Electricity | FALSE | TRUE | 38 | 92.68% | 133 | null | 2025-03-25 11:54:28.699895+00
140 | Floor tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 124 | null | 2025-03-25 11:54:28.699895+00
140 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 51 | 92.73% | 134 | null | 2025-03-25 11:54:28.699895+00
141 | Electric conduits in the wall | 3 | Electricity | TRUE | TRUE | 0 | 0% | 133 | null | 2025-03-25 11:54:28.699895+00
141 | Floor tiling | 5 | Tiling | FALSE | TRUE | 67 | 108.1% | 124 | null | 2025-03-25 11:54:28.699895+00
141 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 60 | 109.1% | 134 | null | 2025-03-25 11:54:28.699895+00
142 | Electric conduits in the wall | 3 | Electricity | TRUE | TRUE | 0 | 0% | 133 | null | 2025-03-25 11:54:28.699895+00
142 | Floor tiling | 5 | Tiling | FALSE | TRUE | 65 | 104.8% | 124 | 142 | 2025-03-25 11:54:28.699895+00
142 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 54 | 98.18% | 134 | null | 2025-03-25 11:54:28.699895+00
143 | Electric conduits in the wall | 3 | Electricity | FALSE | TRUE | 45 | 109.8% | 133 | 143 | 2025-03-25 11:54:28.699895+00
143 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
143 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
144 | Electric conduits in the wall | 4 | Electricity | FALSE | TRUE | 38 | 92.68% | 143 | null | 2025-03-25 11:54:28.699895+00
144 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 50 | 90.91% | 134 | null | 2025-03-25 11:54:28.699895+00
144 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
145 | Electric conduits in the wall | 4 | Electricity | TRUE | TRUE | 0 | 0% | 143 | null | 2025-03-25 11:54:28.699895+00
145 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
145 | Wall tiling | 2 | Tiling | FALSE | TRUE | 29 | 107.4% | 142 | null | 2025-03-25 11:54:28.699895+00
146 | Electric conduits in the wall | 4 | Electricity | FALSE | TRUE | 42 | 102.4% | 143 | null | 2025-03-25 11:54:28.699895+00
146 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
146 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
147 | Electric conduits in the wall | 4 | Electricity | FALSE | TRUE | 42 | 102.4% | 143 | null | 2025-03-25 11:54:28.699895+00
147 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
147 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
148 | Electric conduits in the wall | 4 | Electricity | FALSE | TRUE | 37 | 90.24% | 143 | null | 2025-03-25 11:54:28.699895+00
148 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 53 | 96.36% | 134 | null | 2025-03-25 11:54:28.699895+00
148 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
149 | Electric conduits in the wall | 4 | Electricity | TRUE | TRUE | 0 | 0% | 143 | null | 2025-03-25 11:54:28.699895+00
149 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
149 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
150 | Electric conduits in the wall | 4 | Electricity | FALSE | TRUE | 42 | 102.4% | 143 | 150 | 2025-03-25 11:54:28.699895+00
150 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
150 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
151 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 60 | 109.1% | 134 | null | 2025-03-25 11:54:28.699895+00
151 | Wall tiling | 2 | Tiling | FALSE | TRUE | 25 | 92.59% | 142 | null | 2025-03-25 11:54:28.699895+00
152 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 55 | 100% | 134 | null | 2025-03-25 11:54:28.699895+00
152 | Wall tiling | 2 | Tiling | FALSE | TRUE | 28 | 103.7% | 142 | null | 2025-03-25 11:54:28.699895+00
153 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 56 | 101.8% | 134 | null | 2025-03-25 11:54:28.699895+00
153 | Wall tiling | 2 | Tiling | FALSE | TRUE | 26 | 96.3% | 142 | null | 2025-03-25 11:54:28.699895+00
154 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 56 | 101.8% | 134 | null | 2025-03-25 11:54:28.699895+00
154 | Wall tiling | 2 | Tiling | FALSE | TRUE | 25 | 92.59% | 142 | null | 2025-03-25 11:54:28.699895+00
155 | Partition phase 1 | 5 | Partition | TRUE | TRUE | 0 | 0% | 134 | null | 2025-03-25 11:54:28.699895+00
155 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
156 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 51 | 92.73% | 134 | null | 2025-03-25 11:54:28.699895+00
156 | Wall tiling | 2 | Tiling | FALSE | TRUE | 27 | 100% | 142 | null | 2025-03-25 11:54:28.699895+00
157 | Partition phase 1 | 5 | Partition | FALSE | TRUE | 58 | 105.5% | 134 | 157 | 2025-03-25 11:54:28.699895+00
157 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
158 | Partition phase 3 | 3 | Partition | FALSE | TRUE | 35 | 109.4% | 157 | null | 2025-03-25 11:54:28.699895+00
158 | Pipes in the wall | 5 | Plumbing | FALSE | TRUE | 37 | 100% | 157 | null | 2025-03-25 11:54:28.699895+00
158 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
159 | Partition phase 3 | 3 | Partition | FALSE | TRUE | 31 | 96.88% | 157 | null | 2025-03-25 11:54:28.699895+00
159 | Pipes in the wall | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 157 | null | 2025-03-25 11:54:28.699895+00
159 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
160 | Partition phase 3 | 3 | Partition | FALSE | TRUE | 32 | 100% | 157 | null | 2025-03-25 11:54:28.699895+00
160 | Pipes in the wall | 5 | Plumbing | FALSE | TRUE | 35 | 94.59% | 157 | null | 2025-03-25 11:54:28.699895+00
160 | Wall tiling | 2 | Tiling | FALSE | TRUE | 28 | 103.7% | 142 | null | 2025-03-25 11:54:28.699895+00
161 | Partition phase 3 | 3 | Partition | FALSE | TRUE | 33 | 103.1% | 157 | null | 2025-03-25 11:54:28.699895+00
161 | Pipes in the wall | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 157 | null | 2025-03-25 11:54:28.699895+00
161 | Wall tiling | 2 | Tiling | FALSE | TRUE | 26 | 96.3% | 142 | null | 2025-03-25 11:54:28.699895+00
162 | Partition phase 3 | 3 | Partition | FALSE | TRUE | 30 | 93.75% | 157 | null | 2025-03-25 11:54:28.699895+00
162 | Pipes in the wall | 5 | Plumbing | FALSE | TRUE | 39 | 105.4% | 157 | null | 2025-03-25 11:54:28.699895+00
162 | Wall tiling | 2 | Tiling | FALSE | TRUE | 28 | 103.7% | 142 | null | 2025-03-25 11:54:28.699895+00
163 | Partition phase 3 | 3 | Partition | FALSE | TRUE | 29 | 90.63% | 157 | null | 2025-03-25 11:54:28.699895+00
163 | Pipes in the wall | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 157 | null | 2025-03-25 11:54:28.699895+00
163 | Wall tiling | 2 | Tiling | TRUE | TRUE | 0 | 0% | 142 | null | 2025-03-25 11:54:28.699895+00
164 | Partition phase 3 | 3 | Partition | TRUE | TRUE | 0 | 0% | 157 | null | 2025-03-25 11:54:28.699895+00
164 | Pipes in the wall | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 157 | null | 2025-03-25 11:54:28.699895+00
164 | Wall tiling | 2 | Tiling | FALSE | TRUE | 28 | 103.7% | 142 | null | 2025-03-25 11:54:28.699895+00
165 | Partition phase 3 | 3 | Partition | TRUE | TRUE | 0 | 0% | 157 | null | 2025-03-25 11:54:28.699895+00
165 | Pipes in the wall | 5 | Plumbing | FALSE | TRUE | 34 | 91.89% | 157 | null | 2025-03-25 11:54:28.699895+00
165 | Wall tiling | 2 | Tiling | FALSE | TRUE | 29 | 107.4% | 142 | 165 | 2025-03-25 11:54:28.699895+00
166 | Partition phase 3 | 3 | Partition | FALSE | TRUE | 30 | 93.75% | 157 | 166 | 2025-03-25 11:54:28.699895+00
166 | Pipes in the wall | 5 | Plumbing | TRUE | TRUE | 0 | 0% | 157 | null | 2025-03-25 11:54:28.699895+00
167 | Partition phase 3 | 4 | Partition | FALSE | TRUE | 29 | 90.63% | 166 | null | 2025-03-25 11:54:28.699895+00
167 | Pipes in the wall | 5 | Plumbing | FALSE | TRUE | 36 | 97.3% | 157 | null | 2025-03-25 11:54:28.699895+00
167 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
168 | Partition phase 3 | 4 | Partition | FALSE | TRUE | 32 | 100% | 166 | null | 2025-03-25 11:54:28.699895+00
168 | Pipes in the wall | 5 | Plumbing | FALSE | TRUE | 40 | 108.1% | 157 | 168 | 2025-03-25 11:54:28.699895+00
168 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
169 | Partition phase 3 | 4 | Partition | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
169 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
170 | Partition phase 3 | 4 | Partition | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
170 | Wall tiling | 3 | Tiling | FALSE | TRUE | 25 | 92.59% | 166 | null | 2025-03-25 11:54:28.699895+00
171 | Partition phase 3 | 4 | Partition | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
171 | Wall tiling | 3 | Tiling | FALSE | TRUE | 25 | 92.59% | 166 | null | 2025-03-25 11:54:28.699895+00
172 | Partition phase 3 | 4 | Partition | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
172 | Wall tiling | 3 | Tiling | FALSE | TRUE | 24 | 88.89% | 166 | null | 2025-03-25 11:54:28.699895+00
173 | Partition phase 3 | 4 | Partition | FALSE | TRUE | 30 | 93.75% | 166 | null | 2025-03-25 11:54:28.699895+00
173 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
174 | Partition phase 3 | 4 | Partition | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
174 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
175 | Partition phase 3 | 4 | Partition | FALSE | TRUE | 32 | 100% | 166 | null | 2025-03-25 11:54:28.699895+00
175 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
176 | Partition phase 3 | 4 | Partition | FALSE | TRUE | 34 | 106.2% | 166 | null | 2025-03-25 11:54:28.699895+00
176 | Wall tiling | 3 | Tiling | FALSE | TRUE | 25 | 92.59% | 166 | null | 2025-03-25 11:54:28.699895+00
177 | Partition phase 3 | 4 | Partition | FALSE | TRUE | 33 | 103.1% | 166 | null | 2025-03-25 11:54:28.699895+00
177 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
178 | Partition phase 3 | 4 | Partition | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
178 | Wall tiling | 3 | Tiling | FALSE | TRUE | 29 | 107.4% | 166 | null | 2025-03-25 11:54:28.699895+00
179 | Partition phase 3 | 4 | Partition | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
179 | Wall tiling | 3 | Tiling | FALSE | TRUE | 25 | 92.59% | 166 | null | 2025-03-25 11:54:28.699895+00
180 | Partition phase 3 | 4 | Partition | FALSE | TRUE | 31 | 96.88% | 166 | 180 | 2025-03-25 11:54:28.699895+00
180 | Wall tiling | 3 | Tiling | FALSE | TRUE | 26 | 96.3% | 166 | null | 2025-03-25 11:54:28.699895+00
181 | Partition phase 2 | 5 | Partition | FALSE | TRUE | 52 | 102% | 180 | 181 | 2025-03-25 11:54:28.699895+00
181 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
182 | Electric conduits in the wall | 5 | Electricity | TRUE | TRUE | 0 | 0% | 181 | null | 2025-03-25 11:54:28.699895+00
182 | Wall tiling | 3 | Tiling | FALSE | TRUE | 26 | 96.3% | 166 | null | 2025-03-25 11:54:28.699895+00
183 | Electric conduits in the wall | 5 | Electricity | FALSE | TRUE | 43 | 104.9% | 181 | null | 2025-03-25 11:54:28.699895+00
183 | Wall tiling | 3 | Tiling | FALSE | TRUE | 27 | 100% | 166 | null | 2025-03-25 11:54:28.699895+00
184 | Electric conduits in the wall | 5 | Electricity | FALSE | TRUE | 43 | 104.9% | 181 | null | 2025-03-25 11:54:28.699895+00
184 | Wall tiling | 3 | Tiling | FALSE | TRUE | 25 | 92.59% | 166 | null | 2025-03-25 11:54:28.699895+00
185 | Electric conduits in the wall | 5 | Electricity | TRUE | TRUE | 0 | 0% | 181 | null | 2025-03-25 11:54:28.699895+00
185 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
186 | Electric conduits in the wall | 5 | Electricity | TRUE | TRUE | 0 | 0% | 181 | null | 2025-03-25 11:54:28.699895+00
186 | Wall tiling | 3 | Tiling | TRUE | TRUE | 0 | 0% | 166 | null | 2025-03-25 11:54:28.699895+00
187 | Electric conduits in the wall | 5 | Electricity | TRUE | TRUE | 0 | 0% | 181 | null | 2025-03-25 11:54:28.699895+00
187 | Wall tiling | 3 | Tiling | FALSE | TRUE | 26 | 96.3% | 166 | 187 | 2025-03-25 11:54:28.699895+00
188 | Electric conduits in the wall | 5 | Electricity | FALSE | TRUE | 43 | 104.9% | 181 | null | 2025-03-25 11:54:28.699895+00
188 | Wall tiling | 4 | Tiling | FALSE | TRUE | 29 | 107.4% | 187 | null | 2025-03-25 11:54:28.699895+00
189 | Electric conduits in the wall | 5 | Electricity | FALSE | TRUE | 43 | 104.9% | 181 | null | 2025-03-25 11:54:28.699895+00
189 | Wall tiling | 4 | Tiling | FALSE | TRUE | 25 | 92.59% | 187 | null | 2025-03-25 11:54:28.699895+00
190 | Electric conduits in the wall | 5 | Electricity | FALSE | TRUE | 44 | 107.3% | 181 | 190 | 2025-03-25 11:54:28.699895+00
190 | Wall tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 187 | null | 2025-03-25 11:54:28.699895+00
191 | Partition phase 3 | 5 | Partition | TRUE | TRUE | 0 | 0% | 190 | null | 2025-03-25 11:54:28.699895+00
191 | Wall tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 187 | null | 2025-03-25 11:54:28.699895+00
192 | Partition phase 3 | 5 | Partition | TRUE | TRUE | 0 | 0% | 190 | null | 2025-03-25 11:54:28.699895+00
192 | Wall tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 187 | null | 2025-03-25 11:54:28.699895+00
193 | Partition phase 3 | 5 | Partition | FALSE | TRUE | 34 | 106.2% | 190 | null | 2025-03-25 11:54:28.699895+00
193 | Wall tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 187 | null | 2025-03-25 11:54:28.699895+00
194 | Partition phase 3 | 5 | Partition | TRUE | TRUE | 0 | 0% | 190 | null | 2025-03-25 11:54:28.699895+00
194 | Wall tiling | 4 | Tiling | FALSE | TRUE | 25 | 92.59% | 187 | null | 2025-03-25 11:54:28.699895+00
195 | Partition phase 3 | 5 | Partition | FALSE | TRUE | 33 | 103.1% | 190 | null | 2025-03-25 11:54:28.699895+00
195 | Wall tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 187 | null | 2025-03-25 11:54:28.699895+00
196 | Partition phase 3 | 5 | Partition | TRUE | TRUE | 0 | 0% | 190 | null | 2025-03-25 11:54:28.699895+00
196 | Wall tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 187 | null | 2025-03-25 11:54:28.699895+00
197 | Partition phase 3 | 5 | Partition | TRUE | TRUE | 0 | 0% | 190 | null | 2025-03-25 11:54:28.699895+00
197 | Wall tiling | 4 | Tiling | FALSE | TRUE | 29 | 107.4% | 187 | null | 2025-03-25 11:54:28.699895+00
198 | Partition phase 3 | 5 | Partition | FALSE | TRUE | 31 | 96.88% | 190 | null | 2025-03-25 11:54:28.699895+00
198 | Wall tiling | 4 | Tiling | FALSE | TRUE | 26 | 96.3% | 187 | null | 2025-03-25 11:54:28.699895+00
199 | Partition phase 3 | 5 | Partition | TRUE | TRUE | 0 | 0% | 190 | null | 2025-03-25 11:54:28.699895+00
199 | Wall tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 187 | null | 2025-03-25 11:54:28.699895+00
200 | Partition phase 3 | 5 | Partition | TRUE | TRUE | 0 | 0% | 190 | null | 2025-03-25 11:54:28.699895+00
200 | Wall tiling | 4 | Tiling | FALSE | TRUE | 28 | 103.7% | 187 | null | 2025-03-25 11:54:28.699895+00
201 | Partition phase 3 | 5 | Partition | TRUE | TRUE | 0 | 0% | 190 | null | 2025-03-25 11:54:28.699895+00
201 | Wall tiling | 4 | Tiling | FALSE | TRUE | 25 | 92.59% | 187 | null | 2025-03-25 11:54:28.699895+00
202 | Partition phase 3 | 5 | Partition | FALSE | TRUE | 35 | 109.4% | 190 | null | 2025-03-25 11:54:28.699895+00
202 | Wall tiling | 4 | Tiling | TRUE | TRUE | 0 | 0% | 187 | null | 2025-03-25 11:54:28.699895+00
203 | Partition phase 3 | 5 | Partition | FALSE | TRUE | 30 | 93.75% | 190 | null | 2025-03-25 11:54:28.699895+00
203 | Wall tiling | 4 | Tiling | FALSE | TRUE | 26 | 96.3% | 187 | null | 2025-03-25 11:54:28.699895+00
204 | Partition phase 3 | 5 | Partition | FALSE | TRUE | 32 | 100% | 190 | null | 2025-03-25 11:54:28.699895+00
204 | Wall tiling | 4 | Tiling | FALSE | TRUE | 26 | 96.3% | 187 | null | 2025-03-25 11:54:28.699895+00
205 | Partition phase 3 | 5 | Partition | FALSE | TRUE | 31 | 96.88% | 190 | 205 | 2025-03-25 11:54:28.699895+00
205 | Wall tiling | 4 | Tiling | FALSE | TRUE | 27 | 100% | 187 | null | 2025-03-25 11:54:28.699895+00
206 | Wall tiling | 4 | Tiling | FALSE | TRUE | 25 | 92.59% | 187 | 206 | 2025-03-25 11:54:28.699895+00
207 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
208 | Wall tiling | 5 | Tiling | FALSE | TRUE | 25 | 92.59% | 206 | null | 2025-03-25 11:54:28.699895+00
209 | Wall tiling | 5 | Tiling | FALSE | TRUE | 29 | 107.4% | 206 | null | 2025-03-25 11:54:28.699895+00
210 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
211 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
212 | Wall tiling | 5 | Tiling | FALSE | TRUE | 29 | 107.4% | 206 | null | 2025-03-25 11:54:28.699895+00
213 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
214 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
215 | Wall tiling | 5 | Tiling | FALSE | TRUE | 29 | 107.4% | 206 | null | 2025-03-25 11:54:28.699895+00
216 | Wall tiling | 5 | Tiling | FALSE | TRUE | 27 | 100% | 206 | null | 2025-03-25 11:54:28.699895+00
217 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
218 | Wall tiling | 5 | Tiling | FALSE | TRUE | 29 | 107.4% | 206 | null | 2025-03-25 11:54:28.699895+00
219 | Wall tiling | 5 | Tiling | FALSE | TRUE | 25 | 92.59% | 206 | null | 2025-03-25 11:54:28.699895+00
220 | Wall tiling | 5 | Tiling | FALSE | TRUE | 28 | 103.7% | 206 | null | 2025-03-25 11:54:28.699895+00
221 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
222 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
223 | Wall tiling | 5 | Tiling | FALSE | TRUE | 25 | 92.59% | 206 | null | 2025-03-25 11:54:28.699895+00
224 | Wall tiling | 5 | Tiling | FALSE | TRUE | 28 | 103.7% | 206 | null | 2025-03-25 11:54:28.699895+00
225 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
226 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
227 | Wall tiling | 5 | Tiling | TRUE | TRUE | 0 | 0% | 206 | null | 2025-03-25 11:54:28.699895+00
228 | Wall tiling | 5 | Tiling | FALSE | TRUE | 27 | 100% | 206 | 228 | 2025-03-25 11:54:28.699895+00